## Sheet1
Somaliland Education sector Implementation Action Plan 2017-2021
Annual Indicative Cost
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
ECE
Expand and Increase Access and Equity in ECE | 1.1 | 1.1.1 Conduct ECE awareness raising campaigns at all community levels through local media. | 1.1.1.1 Conduct quarterly ECE awareness raising campaign though madrassas and Imams | 50% of the parents and Madrassas reached through awareness raising compaing on the media | 0 | 180000 | 180000 | 0 | 0 | PHARO Foudation /MOE&HS
|  |  | 1.1.1.2 Engage with parents on the complimenting nature of ECE to Quranic schools | One national Education committee established and casecaded to the regions | 20000 | 20000 | 20000 | 20000 | 20000 | PHARO Foudation /MOE&HS
|  |  | 1.1.1.3 Establish collaboration with Ministry of Religion and Endowment | MOUs between the minitries | 0 | 0 | 0 | 0 | 0 | PHARO Foudation /MOE&HS
|  | 1.1.2 Expansion access of ECE centers in main cities in the six regions | 1.1.2.1 Construct and furnish 31 new ECE centers | 31 ECE centres constructed and furnished. | 0 | 600000 | 480000 | 420000 | 360000 | PHARO Foudation /MOE&HS
Improve the Quality and Relevance of ECE | 1.2 |  | 1.1.2.2 Recruit and train 300 ECE teachers (70% female) | ECE 300 teacher recruited and at least 70% FM trained on ECE teaching methodology and operational | 607500 | 683500 | 683500 | 607500 | 607500 | PHARO Foudation /MOE&HS/SOS/ Private Schools
|  | 1.2.1 Recruit and train ECE teaching workforce | 1.2.1.1 Update and distribute ECE teaching learning Material | ECE t/l materials distributed to the all existing centres | 26040 | 26040 | 26040 | 26040 | 26040 | PHARO Foudation /MOE&HS/SOS/ Private Schools
Improve Internal and External Efficiencies within ECE | 1.3 | 1.3.1 Develop and adopt an ECE policy with minimum standards for ECE schools | 1.3.1.1 Finalize ECE policy framework | Framework and minimum standards | 75000 | 80000 | 75000 | 75000 | 75000 | PHARO Foudation /MOE&HS/SOS/ Private Schools
|  |  | 1.3.1.2 Develop ECE curriculum framework and minimum standards for ECE facilities for national roll-out | roll out the ECE curriculum and reach 3,720 children. | 20000 | 15000 | 15000 | 0 | 0 | PHARO Foudation /MOE&HS/SOS/ Private Schools
Primary
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
Expand and Increase Access and Equity in Primary education | 2.1 | 2.1.1 Improve , expansion and optimization of the number of primary schools and classrooms, while targeting disadvantaged students | 2.1.1.1 Construct 135 Primary schools including special needs , ABE and 5 upper primary boarding schools | contruction of 5 upper primary boarding schools and 135 primary schools, all functional and used for educational purposes | 1500000 | 2500000 | 3000000 | 0 | 3500000
|  |  | 2.1.1.2 Renovate and furnish 340 classes including water and toilet facilities for the target schools | 340 classrooms renovated, furnished and available for use | 77500 | 186000 | 201500 | 62000 | 0
|  |  | 2.1.1.3 Recruit and provide hardship allowance to 975 primary and ABE teachers in rural areas | 975,teachers recruited receive monthly hardship allowance | 936000 | 936000 | 936000 | 936000 | 936000
|  | 2.1.2 Implement equity strategies in primary schools for students, teachers and head teachers for girls and other marginalized groups. | 2.1.1.4 Provide school feeding program to 200 additional primary and ABE schools , | 425 schools get access to feeding programs | 2929183 | 4100856.2 | 4569525.48 | 4756993.192 | 4831980.2768
|  |  | 2.1.1.5 Establish flexible cost effective and alternative learning approaches to complement formal education system | 425 schools with flexible learning programmes operational
|  |  | 2.1.1.6 Provide take home ration to 21,452 additional girls. | 21452 girls get access to take home ration on regular basis | 965340 | 965340 | 965340 | 965340 | 965340
|  |  | 2.1.1.7 Construct 20 girl friendly places in 20 primary schools | 20 GFS constructed and functional | 0 | 75000 | 75000 | 75000 | 75000
|  |  | 2.1.1.8 Recruit 100 special needs education teachers | 189 special needs teachers recruited and operational | 36000 | 72000 | 120000 | 120000 | 120000
|  | 2.2.1 Increase the number of qualified teachers in primary schools. | 2.2.1.1 Recruit new teachers and provide subject matter and pedagogy training to 2,214 in-service primary school teachers | 5347 teachers trained and certified, are in operation to contribute the quality in education | 0 | 1378800 | 442800 | 1534800 | 910800
Priority Objective 2.2: Improve the Quality and Relevance of Primary Education | 2.2 |  | 2.2.1.2 Support school monitoring and supervision thrice quarterly | 50%of primary schools reach minimum standards requirements | 180000 | 180000 | 180000 | 180000 | 180000
|  | 2.2.2 Strengthen the national curriculum for primary education by improving its relevance and delivery taking into account matters of gender, special needs and vulnerable children | 2.2.1.3 Review ABE curriculum to incorporate culturally relevant material for the Pastoralists and nomadic education | inclusive, relevant to culture and environment curriculum in place. | 0 | 70000 | 0 | 0 | 0
|  |  | 2.2.1.4 Review the national curriculum for primary education and improve its delivery taking into account matters of gender, special needs (Standardized sign language) and vulnerable children. | include primary education curriculum with standard sign language for special needs | 0 | 0 | 94000 | 0 | 0
|  |  | 2.2.1.5 Develop and distribute teaching and learning materials (Teachers guide, student work book). | student text book ratio 1;1 | 0 | 118000 | 100000 | 0 | 0
|  |  | 2.2.1.6 Develop teaching and learning supplementary materials | 50% children get access to supplementary material | 0 | 516375 | 631125 | 0 | 0
Improve Internal and External Efficiencies within the Primary School Subsector |  | 2.3.1 Promote of students survival and transition rate | 2.3.1.1 Conduct supervision/ mentoring of teachers to increase contact hours for teaching of students. | increase contact hours to 7 hours per day | 20000 | 20000 | 20000 | 20000 | 20000
| 2.3 |  | 2.3.1.2 Introduce catch up programmes in 20% of government supported classrooms | provide remedial classess atleast 20% of public schools | 40000 | 40000 | 40000 | 40000 | 40000
|  |  | 2.3.1.3 Establish and carry out assessment of student learning outcomes on an annual basis. | carry out assessments on learning outcomes annually | 120000 | 240000 | 360000 | 480000 | 600000
|  | 2.3.2 Strengthen School management | 2.3.2.1 Introduce and operationalize school improvement plans | 50% of the schools develop and operationalize SIP. | 24000 | 48000 | 72000 | 96000 | 120000
|  |  | 2.3.2.2 Organize CEC meetings, and other with parents fora, to follow up student learning outcomes. | a minimum of 3 CEC meetings conducted annually on learning outcomes carried out. | 0 | 75000 | 63000 | 63000 | 63000
|  |  | 2.3.2.3continue the payment primary staff salary | # teaching staff and non teaching staff getting salary on monthly basis | 10015296.72 | 12064899.1394 | 14114501.5588 | 16164103.9782 | 18213706.3976
[5 empty] | 16843319.72 | 23586270.3394 | 25984792.0388 | 25493237.1702 | 30575826.6744 | 122483445.9428
Secondary
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
Priority Objective 3.1: Increase Access and Equity of secondary education |  | 3.1.1 Improve, expansion and optimize of the number of secondary schools and classrooms, while targeting disadvantaged students | 3.1.1.1 Conduct awareness raising campaigns of the importance of secondary school education in the community | Two massive public awareness raising conducted | 0 | 140000 | 120000 | 0 | 0
|  |  | 3.1.1.2 Construct new secondary school in the six regions | 30 secondry schools constructed and operational across the regions of Somaliland 10 schools 2018, 5 schools 2019, 5 chools 2020, 10 schools 2021 | 0 | 1000000 | 500000 | 500000 | 1000000
| 3.1 |  | 3.1.1.3 Renovate and furnish 500 classes including water and toilet facilities for the target schools in the six regions (500*$3,000) | 75 classrooms renovated and furnished | 0 | 600000 | 450000 | 225000 | 225000
|  |  | 3.1.1.3 Construct girl friendly spaces in ten (10) secondary schools across the country | 10 GFS constructed and functional in ten secondary schools | 0 | 60000 | 45000 | 30000 | 15000
|  |  | 3.1.1.4 Generate scholarships for 500 female secondary students from marginalized communities including special needs | 500 females provided with scholarships | 0 | 44000 | 88000 | 176000 | 220000
|  | 3.1.2 Equitably train, recruit, and distribute teachers to ensure the learning of children in rural areas is supported | 3.1.2.1 Recruit and provide hardship allowance to 100 qualified secondary school teachers of mathematics, chemistry, biology and physics, language and social science annually. | 100 teachers recruited and provided with allowances including hardship for rural areas | 120000 | 120000 | 120000 | 120000 | 120000
Priority Objective 3. 2: Improve the Quality and Relevance of Secondary Education |  | 3.2.1 Train teachers in order to meet student's academic needs | 3.2.1.1 Provide annual in service training for secondary teachers on subject matter and pedagogy to 200 teachers per year | 1196 secondary teachers trained and certified | 0 | 135000 | 135000 | 90000 | 90000
|  |  | 3.2.1.2 Conduct school monitoring and supervision and mentoring of teachers on a quarterly basis. | 20 school supervision visits and monitoring conducted | 180000 | 180000 | 180000 | 180000 | 180000
| 3.2 |  | 3.2.1.3 Recruit 100 qualified secondary school teachers of mathematics, chemistry, biology and physics, language and social science annually. | 2958 recruited and working in schools while esisting once are maitained | 156000 | 312000 | 468000 | 624000 | 780000
|  | 3.2.2 Provide adequate and relevant teaching and learning materials for secondary schools including special needs | 3.2.2.1 Review the national curriculum for secondary education, and improve its relevance and delivery taking into account matters of gender, special needs and vulnerable children (including development of teachers guides) | Secondary school curriculum reviewed | 0 | 0 | 105000 | 0 | 0
|  |  | 3.2.2.2 Procure sufficient learning materials including, language and social science text books, science equipment’s and supplementary reading material to 80 secondary schools. | 80 schools provided with textbooks and supplementary materials | 164490 | 1151430 | 657960 | 657960 | 657960
Priority Objective 3.3 : Improve Internal and External Efficiency of the Secondary Subsector |  | 3.3.1 Promote students survival and transition rates | 3.3.1.1. Organize meetings and orient parents, CECs to follow up student learning outcomes By organize monthly meetings with teachers | 120 CECs have capacity to monitor students learning at comes and reports documented | 20000 | 20000 | 20000 | 20000 | 20000
|  |  | 3.3,1,2 Improve student teaching and learning By strictly following contact hours and strength quality assurance process at school level | 1000 schools monitored three times a year by quaity assurance officers | 40000 | 40000 | 40000 | 40000 | 40000
| 3.3 |  | 3.3.1.3 Implement school level formative assessment in 50% of classrooms. | 700 schools have conducted formative assessments. Similar to the format of the summative | 120000 | 240000 | 360000 | 480000 | 600000
|  |  | 3.3.1.4 Introduce afternoon remedial schools programmes | improved firls perfomance and confidence in all publiuc secondary schools | 250000 | 275000 | 325000 | 325000 | 325000
|  |  | 3.3.1.5 Standardize and strengthen student assessment mechanisms / systems to measure learning outcomes | all school implement school level formative assessment, based on assesment approaches in the curriculum framework | 24000 | 48000 | 72000 | 96000 | 120000
|  | 3.3.2 Develop school Improvement Plans to improve achievement of students’ academic quality | 3.3.2.1 Introduce and operationalize school improvement plans | 55% of schools with functional improvement plans. | 2188435.392 | 2636292.5648 | 3084149.7377 | 3532006.9105 | 3979864.0833
[5 empty] | 3262925.392 | 7001722.5648 | 6770109.7377 | 7095966.9105 | 8372824.0833 | 32503548.6884
NFE
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
Encrease Access and Equity of NFE |  | 4.1.1 Expand NFE centers and classrooms | 4.1.1.1 Construct , furnish and equip 90 classes including Family life center facilities | 90 classrooms constructed and furnished | 0 | 400000 | 300000 | 100000 | 100000
|  |  | 4.1.1.2 Renovate 102 NFE classes including water and toilet facilities for the target centers across the regions | 102 classrooms renovated and furnished | 0 | 105000 | 18000 | 15000 | 15000
| 4.1 |  | 4.1.1.3 Improve infrastructure of existing primary schools through rehabilitation projects | 60% of schools/classrooms rehabilitated | 0 | 150000 | 150000 | 150000 | 150000
|  | 4.1.2 Develop and provide appropriate teaching learning material for adult education | 4.1.2.1 Procure appropriate teaching and learning material to all (FLECS centers ) | 50% adult learners get access to supplementary material | 0 | 92920 | 23920 | 23920 | 23920
|  |  | 4.1.2.2 Procure and distribute TLMs to accommodate adult learners | 50% of adult learners access TLMs | 0 | 40000 | 40000 | 40000 | 30000
|  | 4.1.3 Recruit and provide remuneration of NFE teachers for NFE centers | 4.1.3.1 Recruit and remunerate 100 new NFE teachers | 100 facilitators recruited and start teaching adult education programs | 24000 | 42000 | 60000 | 66000 | 72000
|  |  | 4.1.3.2 Recruit adult literacy facilitators. | , 657 adult literacy facilitators recruited. | 0 | 675000 | 675000 | 675000 | 675000
Improve the Quality and Relevance NFE |  | 4.2.1 Provide teacher training to meet NFE academic needs | 4.2.1.1 Provide training on functional literacy and skills for life to 657 NFE instructors | 657 NFE instructors trained | 52560 | 105120 | 52560 | 26280 | 26280
| 4.2 |  | 4.2.1.2 Strengthen supervision and quality assurance process for adult education (NFE) | 50% of NFE centres supervised 3 times | 80000 | 80000 | 80000 | 80000 | 80000
|  | 4.2.2 Provide adequate and relevant NFE teaching and learning materials. | 4.2.2.1 Develop and harmonize, NFE curriculum to incorporate culturally relevant material for NFE | 50% of NFE harmonize, NFE curriculum in place | 0 | 0 | 94000 | 0 | 0
|  |  | 4.2.2.2 Provide sufficient learning materials to all NFE learners including FLECS | adult learns receive TLMs | 0 | 118000 | 100000 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
Improve Internal and External Efficiency of the NFE |  | 4.3.1 Increase retention and promotion in NFE facilities | 4.3.1.1 Standardize and improve student assessment mechanisms / systems to measure learning outcomes | Assessment report in place. | 40000 | 40000 | 40000 | 40000 | 40000 | EU, UNICEF, MoE&HS, USAID, GPE,
| 4.3 |  | 4.3.1.2 Increase NFE learners teaching and learning contact hours | 80 % of teachers comply with the minimum of contact hours per Education Policy. | 21000 | 21000 | 21000 | 21000 | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 4.3.1.3 Conduct capacity building for teachers in life skills training and income generation activities for learners | Conduct capacity building for teachers in life skills training and income generation activities for learners | 21000 | 21000 | 21000 | 21000 | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
[5 empty] | 238560 | 1890040 | 1675480 | 1258200 | 1242200 | 6304480
TVET
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
Improve and Promote access and equity to TVET |  | 5.1.1 Expand TVET centers to main regions | 5.1.1.1 Establish and operationalize new three technical Secondary school in 3 regions | 3 secondary technical schools equipped and functional. | 0 | 3398000 | 3398000 | 3398000 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.1.1.2 Enroll 360 trainees into the new established technical schools annually | about 325 students complete the training sucessfylly | 0 | 432000 | 864000 | 1296000 | 1728000 | MOEHS, GIZ , NGO consotium
|  |  | 5.1.1.3 Provide learning materials to established technical secondary schools | all the functional technical secondary schools have got adequate learning materials. | 0 | 108000 | 216000 | 324000 | 324000 | MOEHS, GIZ , NGO consotium
| 5.1 |  | 5.1.1.4 Provide institutional based and enterprise based trainings to 50 disabled and special needs trainees annually | 50 people with disabilities benefited from enterprise based trainings. | 0 | 65000 | 65000 | 65000 | 65000 | MOEHS, GIZ , NGO consotium
|  | 5.1.2 Promote gender equity in TVET centers, with special attention for girl’s enrollment . | 5.1.2.5 Introduce highly marketable female friendly courses and provide female friendly leaning environment | gender parity in relation to TVET access will reach .06 | 0 | 15000 | 60000 | 0 | 0 | MOEHS, GIZ , NGO consotium
|  | 5.1.3 Implement market demanded EBTVET and IBTEVET | 5.1.3.1 Provide institutional-based training and enterprise-based training to 300 trainees annually | 70% with minimum IT literacy skills | 0 | 300000 | 300000 | 300000 | 300000 | MOEHS, GIZ , NGO consotium
Enhance quality & relevance of TVET trades and strengthen capacity of TVET/TVQA Staff |  | 5.2.1 Strengthen capacity of existing TVET centers to deliver quality training | 5.2.1.1 Strengthen TVET center personnel capabilities to procure equipment and machines through trainings and system development (Procure advanced TVET machines and tools relevant to TVET curricula and repair old machines; Renovate and rehabilitate public TVET institutes). | 80% of functional public Technical institutes have got adequate and relevant equipment and tools for each Course. | 0 | 300000 | 300000 | 300000 | 300000 | MOEHS, GIZ , NGO consotium
|  | 5.2.2 Adopt highly specialized advanced technical skills for learners | 5.2.1.2 Undertake extensive labor market survey to determine advanced and highly employable skills trainings. | labor market survey completed and used to inform TVET programme design | 0 | 70000 | 0 | 0 | 0 | MOEHS, GIZ , NGO consotium
| 5.2 | 5.2.3 Enhance the quality and relevance of TVET through training of instructors and center managers | 52.3.1 Establish TVET instructors’ training department TVET/TVQA departments. | TVET departments established and functioning | 0 | 46600 | 21600 | 26601 | 21602 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.2 Train and produce 200 highly skilled TVET instructors. | 200 TVET instructors trained | 0 | 100000 | 100000 | 100000 | 100000 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.2 Upgrade capacity of TVET center staff through on-the-job training. | provided with center based TVET job training. | 0 | 30000 | 35000 | 40000 | 50000 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.3 Register, assess and accredit TVET centers/Institutes | 90% of existing TVET centers/institutes are accredited By TVQA. | 0 | 30000 | 35000 | 40000 | 50000 | MOEHS, GIZ , NGO consotium
|  | 5.2.4 Improve the relevance and quality of TVET curriculum by adapting and Implementing competency based curriculum | 5.2.3.4 Develop Competence-based Curriculum and implement for all levels. | , 80% of public and private TVET centers/ institutes adapt MOE&HS TVET curricula. | 0 | 300000 | 0 | 0 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.5 Provide on-the-job training and take study tour to TVET staff of MOE&HS | 90% of TVQA and TVET staff complete planned training | 0 | 0 | 0 | 0 | 0 | MOEHS, GIZ , NGO consotium
Improve Internal and External Efficiency of TVET |  | 5.3.1 Standardize and improve assessment and certification of TVET trainees. | 5.3.1.1 Train public TVET examiners and assessors. | . all TVET examinations are standardized and administered By SLNECB | 0 | 300000 | 0 | 0 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.1.2 Establish and operationalize TVET examination unit under SLNECB. | all TVET examinations are standardized and administered By SLNECB | 0 | 10000 | 5000 | 0 | 5000 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.1.3 Strengthen/Develop TVET examination checklist/guideline. | . all TVET examinations are standardized and administered By SLNECB | 0 | 24000 | 24000 | 24000 | 24000 | MOEHS, GIZ , NGO consotium
| 5.3 | 5.3.2 Prepare TVET graduates for employability in the labor market | 5.3.2.1 Establish employment promotion units at TVET centers. | , unites established and functioning | 0 | 10000 | 0 | 0 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.2 Collaborate with MOLSA on linkages of TVET graduates to employers for apprenticeships. | workplace linkages fully established | 0 | 30000 | 0 | 30000 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.3 Provide business startup capital to 120 TVET graduates. | business capital provided to planned number of trainees | 0 | 30000 | 0 | 30000 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.4 Pilot crowdfunding platform in collaboration with MOLSA to enhance availability of funds for business-minded TVET students. | pilot implemented | 0 | 30000 | 0 | 30000 | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.5 Remuneration/admin for TVET center and MOEHS staff (salary costs). |  | 0 | 72000 | 72000 | 72000 | 72000 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.6 Undertake TVET tracer study | tracer studies completed as planned | 0 | 1400899.25 | 1400899.25 | 1400899.25 | 1400899.25 | MOEHS, GIZ , NGO consotium
[5 empty] | 0 | 7101499.25 | 6896499.25 | 7476500.25 | 4440501.25 | 25915000
Higher Education
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
Increase equitable access to higher education in Somaliland |  | 6.1.1 Increase enrolment with an emphasis of girls | 6.1.1.1 Conduct gender needs assessments for intervention | assessments completed and used to shape policy | 20000 | 20000 | 20000 | 10000 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
| 6.1 |  | 6.1.1.2 Provide scholarship grants for 200 girls and disadvantaged students | 200 scholarships granted | 30000 | 60000 | 90000 | 120000 | 150000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.1.1.3 Develop a comprehensive survey of facility expansion needs {higher education minimum standards} | 50% of universities apply gender sensitive minimum standards | 20000 | 20000 | 20000 | 20000 | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 6.2.1 Develop and enforce HE key policy documents and guidelines including quality assurance | 6.2.1.1 Conduct a study on capacity gaps in University human resource | , 50% of lecturers have advanced degrees | 0 | 120000 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
Improve quality and relevance of higher education in Somaliland |  |  | 6.2.1.2 Conduct research and support academic journals | , 5 research papers published | 69058.0693 | 69058.0693 | 69058.0693 | 69058.0693 | 69058.0693 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.3 Develop M&E framework and do regular monitoring | Degree programmes operational with emphasis on entrepreneurial production in marine resources, livestock By products, agriculture, food processing and solar energy | 20000 | 20000 | 20000 | 20000 | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.4 Promote higher education relevance and link with national natural resource, to encourage entrepreneurship | , all 35 Universities publish Annual Reports | 100000 | 100000 | 100000 | 100000 | 100000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.5 Implement HE minimum standards for all HE institutions | Current situation is reviewed and policy is operational to harmonize curriculum framework | 50000 | 50000 | 50000 | 50000 | 50000 | EU, UNICEF, MoE&HS, USAID, GPE,
| 6.2 |  | 6.2.1.6 Adopt standard curriculum framework for Higher education and review for relevance and marketability | Policy is developed and made operational to merge universities | 90000 | 90000 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.7 Develop and implement HE policies including merging universities | , 3 universities or constituent colleges merged. | 0 | 150000 | 160000 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.8 Review and prepare a plan for filling the capacity gaps in the University human resource. | , Capacity Assessment reports prepared and recommendations implemented. | 0 | 120000 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
Improve internal and external efficiency of HE |  | 6.3.1 Improve capacities of Directorate staff | 6.3.1.1 Build directorate staff capacities | , 80% of the university faculty received planned training. | 1182941.9307 | 1682941.9307 | 2182941.9307 | 2682941.9307 | 3182941.9307 | EU, UNICEF, MoE&HS, USAID, GPE,
| 6.3 |  | 6.3.1.2 Construct and furnish the Commission of Higher Education Centre. | , the construction and furnishing of the Office of Commission of completed and building functional | [5 empty] | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.3.1.3 Review remuneration structure for lecturers | , remuneration structure for lecturers harmonized | [5 empty] | EU, UNICEF, MoE&HS, USAID, GPE,
[5 empty] | 1582000 | 2502000 | 2712000 | 3072000 | 3592000 | 13460000
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 | 2018 | 2019 | 2020 | 2021 | resource /Responsibility
Priority Objective 7.1: Improve and strengthen governance and Capacity development for MOEHS system |  | 7.1.1 Strengthen regulatory environment for the sector | 7.1.1.1 Review and harmonize all existing policies, and operationalize the policies. | 20 , policies , manuals, and guidelines are functional and in place | 0 | 200000 | 300000 | 250000 | 250000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.1.2 Strengthen organizational capacity of the ministry of education | 7.1.2.1 Develop all Education subsectors manuals and guidelines for management and operations | , all the required manuals are printed, and distributed for use. | 0 | 100000 | 50000 | 50000 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.1.3 Strengthen capacity of staff to delivery effective services | 7.1.3.1 Carry out HRD needs assessment and competencies at all levels of the management system (central down to school) | By 2018, needs assessment completed and used to shape capacity development programme | 0 | 30000 | 0 | 30000 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.1.3.2 Organize HRM orientation for MOEHS staff | at least 70% of MOEHS staff received HRM information | 0 | 0 | 150000 | 100000 | 100000 | EU, UNICEF, MoE&HS, USAID, GPE,
| 7.1 |  | 7.1.3.3 Develop long-term, on-going capacity building strategy for staff at all levels based on the capacity gaps assessment report | capacity building strategy operational | 0 | 294000 | 294000 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.1.3.4 Recruit Local and international technical advisors for NFE, planning, teacher training, curriculum, TVET and Quality assurance, and a Chief Technical Advisor for Higher Education. | 70 of HODs management capacity improved | 0 | 378000 | 378000 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | Provide targeted training to upgrade the technical competence of selected staff. | 30 MOEHS Officials acquired technical knowledge | 0 | 15000 | 15000 | 15000 | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.1.3.5 Remuneration/basic pay for MOEHE staff (salary and allowances). |  | 286133.3333 | 344689.7185 | 403246.1037 | 461802.4888 | 520358.874 | EU, UNICEF, MoE&HS, USAID, GPE,
Build the institutional capacity of curriculum centre | 7.2 |  | 7.1.3.6 MOEHS admin and recurrent annual costs |  | 4612738.5467 | 5556722.5693 | 6500706.5919 | 7444690.6145 | 8388674.6371 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.2.1 Upgrade curriculum centre physical facilities and resources | 7.2.1.1.Provide essential equipment's and material for printing facilities. | well equipped curriculum institute in place | 0 | 400000 | 25000 | 25000 | 25000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.2.1.2 Renovate and expand the curriculum Institute with adequate working space. | Curriculum institute constructed ,fully equipped and functional | 0 | 375000 | 375000 | 375000 | 375000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.2.2 Increase human resource capacities of the curriculum centre | 7.2.2.1 Recruit and train subject specialists for all education subsectors | all required curriculum specialists Available | 0 | 140400 | 140400 | 667520 | 140400 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | Recruit a team of subject panelist and curriculum developers to build capacities of the Curriculum Institute. | well equipped curriculum institute in place | 0 | 400000 | 25000 | 25000 | 25000 | EU, UNICEF, MoE&HS, USAID, GPE,
Establish full functioning of Somaliland National College of education | 7.3 | 7.3.1 Establish the Somaliland National College of Education | 7.3.1.1 Complete and implement SNCE master plan | National teacher training institute constructed ,fully equipped and functional | 1000000 | 750000 | 750000 | 750000 | 750000 | EU, UNICEF, MoE&HS, USAID, GPE,
Promote and Maintain evidence based EMIS Data for all education subsectors | 7.4 | 7.4.1 Strengthen Education Management Information System (EMIS) | 7.4.1.1 Collect EMIS data on yearly basis for education subsectors (rolling out) | Evidence based EMIS system in place and functional | 200000 | 210000 | 220500 | 231525 | 243101.25 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.4.1.2 Decentralize the EMIS system including training of education personnel at subnational level | All districts have functioning EMIS systems in place | 50000 | 90000 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.4.1.3 Print and disseminate EMIS report to all subnational education offices | Annually EMIS reports distributed to subnational offices | 10000 | 10000 | 10000 | 10000 | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.4.1.4 Update school management records | Annually school management records updated | 30000 | 30000 | 30000 | 30000 | 30000 | EU, UNICEF, MoE&HS, USAID, GPE,
Decentralize primary education functions to the local governments | 7.5 | 7.5.1 Strengthen the policy framework for decentralization of education services | 7.5.1.1 Develop regulatory framework for decentralizing education services | primary education service delivery contribution of Local government increased to 10% | 0 | 10000 | 10000 | 10000 | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.1.2 Develop framework for local government revenue generation for domestic financing of education services | , a framework for domestic financing of education services is operational. | 0 | 0 | 12000 | 12000 | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.5.2 Expand education decentralization service delivery for new district councils with JPLG | 7.5.2.1 Select pilot district councils to implement decentralized education functions | , all 14 districts are benefiting from decentralization policy. | 0 | 20000 | 20000 | 25000 | 25000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.2.2 Conduct capacity assessment for district councils | By 2019, capacity assessment completed and used to inform decentralization policy | 0 | 30000 | 30000 | 30000 | 35000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.2.3 Conduct monitoring and oversight for primary education decentralized functions to the local governments | , all district conduct monthly monitoring visits to schools. | 0 | 10000 | 10000 | 10000 | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.2.4 Conduct education sector decentralization coordination meetings | , the education sector decentralization coordination meetings | 700000 | 756000 | 816480 | 881798.4 | 952342.272 | EU, UNICEF, MoE&HS, USAID, GPE,
Implement reliable and effective annual national Examinations. | 7.6 | 7.6.1 Strengthen the capacity of Somaliland National Examination board | 7.6.1.1 Conduct examinations and produce annual reports | By the end of 2021, 100% of learners sit national Examinations and reports disseminated publicly | 700000 | 756000 | 816480 | 881798.4 | 952342.272 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.1.2 Construct and furnish two Exam setting exam halls, data room for exam center. | By the end of 2021, exam halls will be constructed and fully furnished | 0 | 80000 | 80000 | 33000 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.1.3 Construct and furnish eastern regions exam center in Buroa | By the end of 2021, eastern regions Exam centre in Buroa | 0 | 65000 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.1.4 Conduct country-wide awareness raising on exam cheating and fraud | By the end of 2021, all regions participated in capacity building sessions on fraud and cheating. | 0 | 20000 | 20000 | 20000 | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.6.2 Strengthen data management systems of examination board | 7.6.2.1 Update evaluation system so that formative examinations form a component of overall final student learning assessments, rather than relying only on one data point (i.e. final exams) | By the end of 2021, five formative assessment should be conducted | 0 | 15000 | 15000 | 15000 | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.2.2 Establish Exam Data Bank, permanent subject heads and experts | By the end of 2021, 17 subject experts in place and 1 central Data Bank established. | 0 | 108000 | 108000 | 108000 | 108000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.2.3 Remuneration for MOE&HS exam center technical and management team (staff salary costs). |  | 264000 | 264000 | 264000 | 264000 | 264000 | EU, UNICEF, MoE&HS, USAID, GPE,
Ensure that children access education in safe and protected learning environments in situations of emergency | 7.7 | 7.7.1 Strengthen resilience of education system to ensure continuation of education services before, during and after the emergencies. | 7.7.1.1 Develop and review education in emergency comprehensive contingency plan including capacity development on school safety | timely response to emergency situations | 0 | 3000 | 3000 | 3000 | 3000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.2 Conduct rapid education in emergency assessment | timely up to date rapid assessment reports | 0 | 20000 | 20000 | 20000 | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.3 Provide EIE training for MOE staff at all levels | 200 central, regional and districts MOE and trained | 0 | 12000 | 9000 | 8000 | 9000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.4 Preposition a package of education supplies for education in emergency | , 50% of education supplies prepositioned to response in high risk areas | 800000 | 800000 | 800000 | 800000 | 800000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.5 Provide contingency funds for EiE | government mobilized and programmes emergency funds | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.7.2 Conduct social mobilization campaign, and establish a coordination mechanism for Education in Emergency. | 7.7.2.1 Establish strong education in emergency coordination system with in ESC, government, and actors. | , EiE is a regular agenda of the coordination meeting at the Ministry of Education | 0 | 0 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.2.2 Conduct regular education in emergency coordination meetings with cluster partners. | , 50 national EIE WG meetings held (10 per year over 5 years) | 0 | 0 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.2.3 Advocate and raise awareness to CEC, Head teachers, and communities | , 75% CECs communities sensitized on EIE management. | 0 | 0 | 0 | 0 | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
[5 empty] | 10652871.88 | 14292812.2878 | 14700812.6955 | 15587134.9033 | 16106219.3051 | 71339851.0717

## Sheet3
Provide school feeding program to 200 additional primary and ABE schools , | 2929183 | 0 | 0 | 0 | 0 | 2929183
Provide take home ration to 21,452 additional girls. | 965340 | 965340 | 965340 | 965340 | 965340 | 4826700
Construct 20 girl friendly places in 20 primary schools | 0 | 75000 | 75000 | 75000 | 75000 | 300000
Recruit 100 special needs education teachers | 36000 | 72000 | 120000 | 120000 | 120000 | 468000

## Action plan on quaterly basis
Somaliland Education sector Implementation Action Plan 2017-2021
Annual Indicative Cost
Priority objective | Priority Code | Strategies | Activities | Targets | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 |  |  |  |  | resource /Responsibility
EARLY CHILDHOOD EDUCATION |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Total cost for 2017 | Q1 | Q2 | Q3 | Q4 | Total cost 2018 | Q1 | Q2 | Q3 | Q4 | Total cost for 2019 | Q1 | Q2 | Q3 | Q4 | total cost for 2020 | Q1 | Q2 | Q3 | Q4 | Total cost for 2021
Expand and Increase Access and Equity in ECE | 1.1 | 1.1.1 Conduct ECE awareness raising campaigns at all community levels through local media. | 1.1.1.1 Conduct quarterly ECE awareness raising campaign though madrassas and Imams | 50% of the parents and Madrassas reached through awareness raising compaing on the media |  |  | X | X | 0 |  |  | X |  | 180000 |  |  | X |  | 180000 |  |  | X |  | 0 |  |  | X |  | 0 | PHARO Foudation /MOE&HS
|  |  | 1.1.1.2 Engage with parents on the complimenting nature of ECE to Quranic schools | One national Education committee established and casecaded to the regions |  |  |  | X | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 | PHARO Foudation /MOE&HS
|  |  | 1.1.1.3 Establish collaboration with Ministry of Religion and Endowment | MOUs between the minitries | X | X | X | X | 0 | X | X | X |  | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | PHARO Foudation /MOE&HS
|  | 1.1.2 Expansion access of ECE centers in main cities in the six regions | 1.1.2.1 Construct and furnish 31 new ECE centers | 31 ECE centres constructed and furnished. |  |  |  |  | 0 |  | X | X |  | 600000 |  | X | X |  | 480000 |  | X | X |  | 420000 | X |  |  |  | 360000 | PHARO Foudation /MOE&HS
Improve the Quality and Relevance of ECE | 1.2 |  | 1.1.2.2 Recruit and train 300 ECE teachers (70% female) | ECE 300 teacher recruited and at least 70% FM trained on ECE teaching methodology and operational |  |  | X |  | 607500 |  | X | X |  | 683500 |  | X |  |  | 683500 |  | X |  |  | 607500 |  | X |  |  | 607500 | PHARO Foudation /MOE&HS/SOS/ Private Schools
|  | 1.2.1 Recruit and train ECE teaching workforce | 1.2.1.1 Update and distribute ECE teaching learning Material | ECE t/l materials distributed to the all existing centres |  | X | X |  | 26040 | X |  | X |  | 26040 | X |  | X |  | 26040 | X |  | X |  | 26040 | X |  | X |  | 26040 | PHARO Foudation /MOE&HS/SOS/ Private Schools
Improve Internal and External Efficiencies within ECE | 1.3 | 1.3.1 Develop and adopt an ECE policy with minimum standards for ECE schools | 1.3.1.1 Finalize ECE policy framework | Framework and minimum standards |  |  |  |  | 75000 |  | X | X |  | 80000 |  |  |  |  | 75000 |  |  |  |  | 75000 |  | X | X |  | 75000 | PHARO Foudation /MOE&HS/SOS/ Private Schools
|  |  | 1.3.1.2 Develop ECE curriculum framework and minimum standards for ECE facilities for national roll-out | roll out the ECE curriculum and reach 3,720 children. |  |  |  | X | 20000 | X | X | X | X | 15000 | X | X |  |  | 15000 |  |  |  |  | 0 |  |  |  |  | 0 | PHARO Foudation /MOE&HS/SOS/ Private Schools
PRIMARY EDUCATION
Priority objective | Priority Code | Strategies | Activities | Targets |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 | resource /Responsibility
Expand and Increase Access and Equity in Primary education | 2.1 | 2.1.1 Improve , expansion and optimization of the number of primary schools and classrooms, while targeting disadvantaged students | 2.1.1.1 Construct 135 Primary schools including special needs , ABE and 5 upper primary boarding schools | contruction of 5 upper primary boarding schools and 135 primary schools, all functional and used for educational purposes | X | X |  |  | 1500000 | X | X |  |  | 2500000 | X | X |  |  | 3000000 |  |  |  |  | 0 |  |  |  |  | 3500000
|  |  | 2.1.1.2 Renovate and furnish 340 classes including water and toilet facilities for the target schools | 340 classrooms renovated, furnished and available for use | X | X |  |  | 77500 | X | X |  |  | 186000 | X | X |  |  | 201500 |  | X | X |  | 62000 |  |  |  |  | 0
|  |  | 2.1.1.3 Recruit and provide hardship allowance to 975 primary and ABE teachers in rural areas | 975,teachers recruited receive monthly hardship allowance |  |  | X | X | 936000 | X | X | X | X | 936000 | X | X | X | X | 936000 | X | X | X | X | 936000 | X | X | X | X | 936000
|  | 2.1.2 Implement equity strategies in primary schools for students, teachers and head teachers for girls and other marginalized groups. | 2.1.1.4 Provide school feeding program to 200 additional primary and ABE schools , | 425 schools get access to feeding programs | X |  | X | X | 2929183 | X |  | X | X | 4100856.2 | X |  | X | X | 4569525.48 | X |  | X | X | 4756993.192 | X |  | X | X | 4831980.2768
|  |  | 2.1.1.5 Establish flexible cost effective and alternative learning approaches to complement formal education system | 425 schools with flexible learning programmes operational |  |  | X |  |  |  |  | X |  |  |  |  | X |  |  |  |  | X |  |  |  |  | X
|  |  | 2.1.1.6 Provide take home ration to 21,452 additional girls. | 21452 girls get access to take home ration on regular basis | X |  | X | X | 965340 | X |  | X | X | 965340 | X |  | X | X | 965340 | X |  | X | X | 965340 | X |  | X | X | 965340
|  |  | 2.1.1.7 Construct 20 girl friendly places in 20 primary schools | 20 GFS constructed and functional |  |  |  |  | 0 |  | X |  |  | 75000 |  | X |  |  | 75000 |  | X |  |  | 75000 |  | X |  |  | 75000
|  |  | 2.1.1.8 Recruit 100 special needs education teachers | 189 special needs teachers recruited and operational |  |  | X | X | 36000 | X |  |  |  | 72000 | X |  |  |  | 120000 | X |  |  |  | 120000 | X |  |  |  | 120000
|  | 2.2.1 Increase the number of qualified teachers in primary schools. | 2.2.1.1 Recruit new teachers and provide subject matter and pedagogy training to 2,214 in-service primary school teachers | 5347 teachers trained and certified, are in operation to contribute the quality in education |  |  |  |  | 0 | X | X |  |  | 1378800 | X | X |  |  | 442800 | X | X |  |  | 1534800 | X | X |  |  | 910800
Priority Objective 2.2: Improve the Quality and Relevance of Primary Education | 2.2 |  | 2.2.1.2 Support school monitoring and supervision thrice quarterly | 50%of primary schools reach minimum standards requirements | X |  | X | X | 180000 | X |  | X | X | 180000 | X |  | X | X | 180000 | X |  | X | X | 180000 | X |  | X | X | 180000
|  | 2.2.2 Strengthen the national curriculum for primary education by improving its relevance and delivery taking into account matters of gender, special needs and vulnerable children | 2.2.1.3 Review ABE curriculum to incorporate culturally relevant material for the Pastoralists and nomadic education | inclusive, relevant to culture and environment curriculum in place. |  |  |  |  | 0 |  |  |  | X | 70000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
|  |  | 2.2.1.4 Review the national curriculum for primary education and improve its delivery taking into account matters of gender, special needs (Standardized sign language) and vulnerable children. | include primary education curriculum with standard sign language for special needs |  |  |  |  | 0 |  |  |  |  | 0 |  |  | X | X | 94000 |  |  |  |  | 0 |  |  |  |  | 0
|  |  | 2.2.1.5 Develop and distribute teaching and learning materials (Teachers guide, student work book). | student text book ratio 1;1 |  |  |  |  | 0 | X |  |  | X | 118000 |  |  |  |  | 100000 |  |  |  |  | 0 |  |  |  |  | 0
|  |  | 2.2.1.6 Develop teaching and learning supplementary materials | 50% children get access to supplementary material |  |  |  |  | 0 |  |  | X |  | 516375 |  | X |  |  | 631125 |  |  |  |  | 0 |  |  |  |  | 0
Improve Internal and External Efficiencies within the Primary School Subsector |  | 2.3.1 Promote of students survival and transition rate | 2.3.1.1 Conduct supervision/ mentoring of teachers to increase contact hours for teaching of students. | increase contact hours to 7 hours per day |  |  |  |  | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000
| 2.3 |  | 2.3.1.2 Introduce catch up programmes in 20% of government supported classrooms | provide remedial classess atleast 20% of public schools |  |  | X |  | 40000 |  |  | X |  | 40000 |  |  | X |  | 40000 |  |  | X |  | 40000 |  | X |  |  | 40000
|  |  | 2.3.1.3 Establish and carry out assessment of student learning outcomes on an annual basis. | carry out assessments on learning outcomes annually |  | X |  |  | 120000 |  | X |  |  | 240000 |  | X |  |  | 360000 |  | X |  |  | 480000 |  | X |  |  | 600000
|  | 2.3.2 Strengthen School management | 2.3.2.1 Introduce and operationalize school improvement plans | 50% of the schools develop and operationalize SIP. |  |  | X |  | 24000 |  |  | X |  | 48000 |  |  | X |  | 72000 |  |  | X |  | 96000 |  |  | X |  | 120000
|  |  | 2.3.2.2 Organize CEC meetings, and other with parents fora, to follow up student learning outcomes. | a minimum of 3 CEC meetings conducted annually on learning outcomes carried out. | X |  | X | X | 0 | X |  | X | X | 75000 | X |  | X | X | 63000 | X |  | X | X | 63000 | X |  | X | X | 63000
|  |  | 2.3.2.3continue the payment primary staff salary | # teaching staff and non teaching staff getting salary on monthly basis |  |  |  |  | 10015296.72 |  |  |  |  | 12064899.1394 |  |  |  |  | 14114501.5588 |  |  |  |  | 16164103.9782 |  |  |  |  | 18213706.3976
[9 empty] | 16843319.72 |  |  |  |  | 23586270.3394 |  |  |  |  | 25984792.0388 |  |  |  |  | 25493237.1702 |  |  |  |  | 30575826.6744 | 122483445.9428
SECONDARY EDUCATION
Priority objective | Priority Code | Strategies | Activities | Targets |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 | resource /Responsibility
Priority Objective 3.1: Increase Access and Equity of secondary education |  | 3.1.1 Improve, expansion and optimize of the number of secondary schools and classrooms, while targeting disadvantaged students | 3.1.1.1 Conduct awareness raising campaigns of the importance of secondary school education in the community | Two massive public awareness raising conducted | X |  | X |  | 0 | X |  | X |  | 140000 | X |  | X |  | 120000 | X |  | X |  | 0 | X |  | X |  | 0
|  |  | 3.1.1.2 Construct new secondary school in the six regions | 30 secondry schools constructed and operational across the regions of Somaliland 10 schools 2018, 5 schools 2019, 5 chools 2020, 10 schools 2021 |  |  |  |  | 0 | X | X |  |  | 1000000 | X | X |  |  | 500000 | X | X |  |  | 500000 | X | X |  |  | 1000000
| 3.1 |  | 3.1.1.3 Renovate and furnish 500 classes including water and toilet facilities for the target schools in the six regions (500*$3,000) | 75 classrooms renovated and furnished |  |  |  |  | 0 | X | X |  |  | 600000 | X | X |  |  | 450000 | X | X |  |  | 225000 | X | X |  |  | 225000
|  |  | 3.1.1.3 Construct girl friendly spaces in ten (10) secondary schools across the country | 10 GFS constructed and functional in ten secondary schools |  |  |  |  | 0 |  |  |  |  | 60000 |  |  |  |  | 45000 |  |  |  |  | 30000 |  |  |  |  | 15000
|  |  | 3.1.1.4 Generate scholarships for 500 female secondary students from marginalized communities including special needs | 500 females provided with scholarships |  |  |  |  | 0 | X | X | X | X | 44000 | X | X | X | X | 88000 | X | X | X | X | 176000 | X | X | X | X | 220000
|  | 3.1.2 Equitably train, recruit, and distribute teachers to ensure the learning of children in rural areas is supported | 3.1.2.1 Recruit and provide hardship allowance to 100 qualified secondary school teachers of mathematics, chemistry, biology and physics, language and social science annually. | 100 teachers recruited and provided with allowances including hardship for rural areas |  |  | X | X | 120000 | X | X | X | X | 120000 | X | X | X | X | 120000 | X | X | X | X | 120000 | X | X | X | X | 120000
Priority Objective 3. 2: Improve the Quality and Relevance of Secondary Education |  | 3.2.1 Train teachers in order to meet student's academic needs | 3.2.1.1 Provide annual in service training for secondary teachers on subject matter and pedagogy to 200 teachers per year | 1196 secondary teachers trained and certified |  |  | X |  | 0 |  | X | X |  | 135000 |  | X | X |  | 135000 |  | X | X |  | 90000 |  | X | X |  | 90000
|  |  | 3.2.1.2 Conduct school monitoring and supervision and mentoring of teachers on a quarterly basis. | 20 school supervision visits and monitoring conducted | X | X | X | X | 180000 | X | X | X | X | 180000 | X | X | X | X | 180000 | X | X | X | X | 180000 | X | X | X | X | 180000
| 3.2 |  | 3.2.1.3 Recruit 100 qualified secondary school teachers of mathematics, chemistry, biology and physics, language and social science annually. | 2958 recruited and working in schools while esisting once are maitained | X |  |  |  | 156000 | X |  |  |  | 312000 | X |  |  |  | 468000 | X |  |  |  | 624000 | X |  |  |  | 780000
|  | 3.2.2 Provide adequate and relevant teaching and learning materials for secondary schools including special needs | 3.2.2.1 Review the national curriculum for secondary education, and improve its relevance and delivery taking into account matters of gender, special needs and vulnerable children (including development of teachers guides) | Secondary school curriculum reviewed |  |  |  |  | 0 |  |  |  |  | 0 |  |  | X | X | 105000 |  |  |  |  | 0 |  |  |  |  | 0
|  |  | 3.2.2.2 Procure sufficient learning materials including, language and social science text books, science equipment’s and supplementary reading material to 80 secondary schools. | 80 schools provided with textbooks and supplementary materials |  |  | X | X | 164490 |  | X | X |  | 1151430 |  | X | X |  | 657960 |  | X | X |  | 657960 |  | X | X |  | 657960
Priority Objective 3.3 : Improve Internal and External Efficiency of the Secondary Subsector |  | 3.3.1 Promote students survival and transition rates | 3.3.1.1. Organize meetings and orient parents, CECs to follow up student learning outcomes By organize monthly meetings with teachers | 120 CECs have capacity to monitor students learning at comes and reports documented | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000
|  |  | 3.3,1,2 Improve student teaching and learning By strictly following contact hours and strength quality assurance process at school level | 1000 schools monitored three times a year by quaity assurance officers | X | X | X | X | 40000 | X | X | X | X | 40000 | X | X | X | X | 40000 | X | X | X | X | 40000 | X | X | X | X | 40000
| 3.3 |  | 3.3.1.3 Implement school level formative assessment in 50% of classrooms. | 700 schools have conducted formative assessments. Similar to the format of the summative |  | X |  |  | 120000 |  | X |  |  | 240000 |  | X |  |  | 360000 |  | X |  |  | 480000 |  | X |  |  | 600000
|  |  | 3.3.1.4 Introduce afternoon remedial schools programmes | improved firls perfomance and confidence in all publiuc secondary schools | X | X |  | X | 250000 | X | X |  | X | 275000 | X | X |  | X | 325000 | X | X |  | X | 325000 | X | X |  | X | 325000
|  |  | 3.3.1.5 Standardize and strengthen student assessment mechanisms / systems to measure learning outcomes | all school implement school level formative assessment, based on assesment approaches in the curriculum framework |  |  |  | X | 24000 |  |  |  | X | 48000 |  |  |  | X | 72000 |  |  |  | X | 96000 |  |  |  | X | 120000
|  | 3.3.2 Develop school Improvement Plans to improve achievement of students’ academic quality | 3.3.2.1 Introduce and operationalize school improvement plans | 55% of schools with functional improvement plans. | X | X |  | X | 2188435.392 | X | X |  | X | 2636292.5648 | X | X |  | X | 3084149.7377 | X | X |  | X | 3532006.9105 | X | X |  | X | 3979864.0833
[9 empty] | 3262925.392 |  |  |  |  | 7001722.5648 |  |  |  |  | 6770109.7377 |  |  |  |  | 7095966.9105 |  |  |  |  | 8372824.0833 | 32503548.6884
NON-FORMAL EDUCATION
Priority objective | Priority Code | Strategies | Activities | Targets |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 | resource /Responsibility
Encrease Access and Equity of NFE |  | 4.1.1 Expand NFE centers and classrooms | 4.1.1.1 Construct , furnish and equip 90 classes including Family life center facilities | 90 classrooms constructed and furnished |  |  |  |  | 0 | X | X |  |  | 400000 | X | X |  |  | 300000 | X | X |  |  | 100000 | X | X |  |  | 100000
|  |  | 4.1.1.2 Renovate 102 NFE classes including water and toilet facilities for the target centers across the regions | 102 classrooms renovated and furnished |  |  |  |  | 0 | X | X |  |  | 105000 | X | X |  |  | 18000 | X | X |  |  | 15000 | X | X |  |  | 15000
| 4.1 |  | 4.1.1.3 Improve infrastructure of existing primary schools through rehabilitation projects | 60% of schools/classrooms rehabilitated |  |  |  |  | 0 | X | X |  |  | 150000 | X | X |  |  | 150000 | X | X |  |  | 150000 | X | X |  |  | 150000
|  | 4.1.2 Develop and provide appropriate teaching learning material for adult education | 4.1.2.1 Procure appropriate teaching and learning material to all (FLECS centers ) | 50% adult learners get access to supplementary material |  |  | X |  | 0 |  |  | X |  | 92920 |  |  | X |  | 23920 |  |  | X |  | 23920 |  |  | X |  | 23920
|  |  | 4.1.2.2 Procure and distribute TLMs to accommodate adult learners | 50% of adult learners access TLMs |  |  | X |  | 0 |  |  | X |  | 40000 |  |  | X |  | 40000 |  |  | X |  | 40000 |  |  | X |  | 30000
|  | 4.1.3 Recruit and provide remuneration of NFE teachers for NFE centers | 4.1.3.1 Recruit and remunerate 100 new NFE teachers | 100 facilitators recruited and start teaching adult education programs | X |  |  |  | 24000 | X |  |  |  | 42000 | X |  |  |  | 60000 | X |  |  |  | 66000 | X |  |  |  | 72000
|  |  | 4.1.3.2 Recruit adult literacy facilitators. | , 657 adult literacy facilitators recruited. |  |  |  |  | 0 | X |  |  |  | 675000 | X |  |  |  | 675000 | X |  |  |  | 675000 | X |  |  |  | 675000
Improve the Quality and Relevance NFE |  | 4.2.1 Provide teacher training to meet NFE academic needs | 4.2.1.1 Provide training on functional literacy and skills for life to 657 NFE instructors | 657 NFE instructors trained |  | X | X |  | 52560 |  | X | X |  | 105120 |  | X | X |  | 52560 |  | X | X |  | 26280 |  | X | X |  | 26280
| 4.2 |  | 4.2.1.2 Strengthen supervision and quality assurance process for adult education (NFE) | 50% of NFE centres supervised 3 times | X | X | X | X | 80000 | X | X | X | X | 80000 | X | X | X | X | 80000 | X | X | X | X | 80000 | X | X | X | X | 80000
|  | 4.2.2 Provide adequate and relevant NFE teaching and learning materials. | 4.2.2.1 Develop and harmonize, NFE curriculum to incorporate culturally relevant material for NFE | 50% of NFE harmonize, NFE curriculum in place |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | X | 94000 |  |  |  |  | 0 |  |  |  |  | 0
|  |  | 4.2.2.2 Provide sufficient learning materials to all NFE learners including FLECS | adult learns receive TLMs |  |  | X | X | 0 |  |  | X | X | 118000 |  |  | X | X | 100000 |  |  | X | X | 0 |  |  | X | X | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
Improve Internal and External Efficiency of the NFE |  | 4.3.1 Increase retention and promotion in NFE facilities | 4.3.1.1 Standardize and improve student assessment mechanisms / systems to measure learning outcomes | Assessment report in place. |  |  |  | X | 40000 |  |  |  | X | 40000 |  |  |  | X | 40000 |  |  |  | X | 40000 |  |  |  | X | 40000 | EU, UNICEF, MoE&HS, USAID, GPE,
| 4.3 |  | 4.3.1.2 Increase NFE learners teaching and learning contact hours | 80 % of teachers comply with the minimum of contact hours per Education Policy. | X | X | X | X | 21000 | X | X | X | X | 21000 | X | X | X | X | 21000 | X | X | X | X | 21000 |  |  |  |  | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 4.3.1.3 Conduct capacity building for teachers in life skills training and income generation activities for learners | Conduct capacity building for teachers in life skills training and income generation activities for learners |  |  | X | X | 21000 |  |  | X | X | 21000 |  |  | X | X | 21000 |  |  | X | X | 21000 |  |  | X | X | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
[9 empty] | 238560 |  |  |  |  | 1890040 |  |  |  |  | 1675480 |  |  |  |  | 1258200 |  |  |  |  | 1242200 | 6304480
TVET
Priority objective | Priority Code | Strategies | Activities | Targets |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 | resource /Responsibility
Improve and Promote access and equity to TVET |  | 5.1.1 Expand TVET centers to main regions | 5.1.1.1 Establish and operationalize new three technical Secondary school in 3 regions | 3 secondary technical schools equipped and functional. |  |  |  |  | 0 |  | X |  |  | 3398000 |  | X |  |  | 3398000 |  | X |  |  | 3398000 |  | X |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.1.1.2 Enroll 360 trainees into the new established technical schools annually | about 325 students complete the training sucessfylly |  |  |  |  | 0 | X |  |  |  | 432000 | X |  |  |  | 864000 | X |  |  |  | 1296000 | X |  |  |  | 1728000 | MOEHS, GIZ , NGO consotium
|  |  | 5.1.1.3 Provide learning materials to established technical secondary schools | all the functional technical secondary schools have got adequate learning materials. |  |  |  |  | 0 |  |  | X |  | 108000 |  |  | X |  | 216000 |  |  | X |  | 324000 |  |  | X |  | 324000 | MOEHS, GIZ , NGO consotium
| 5.1 |  | 5.1.1.4 Provide institutional based and enterprise based trainings to 50 disabled and special needs trainees annually | 50 people with disabilities benefited from enterprise based trainings. | X | X | X | X | 0 | X | X | X |  | 65000 | X | X | X | X | 65000 | X | X | X | X | 65000 | X | X | X | X | 65000 | MOEHS, GIZ , NGO consotium
|  | 5.1.2 Promote gender equity in TVET centers, with special attention for girl’s enrollment . | 5.1.2.5 Introduce highly marketable female friendly courses and provide female friendly leaning environment | gender parity in relation to TVET access will reach .06 |  |  |  |  | 0 | X |  |  |  | 15000 | X |  |  |  | 60000 | X |  |  |  | 0 | X |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  | 5.1.3 Implement market demanded EBTVET and IBTEVET | 5.1.3.1 Provide institutional-based training and enterprise-based training to 300 trainees annually | 70% with minimum IT literacy skills |  | X | X |  | 0 |  | X | X |  | 300000 |  | X | X |  | 300000 |  | X | X |  | 300000 |  | X | X |  | 300000 | MOEHS, GIZ , NGO consotium
Enhance quality & relevance of TVET trades and strengthen capacity of TVET/TVQA Staff |  | 5.2.1 Strengthen capacity of existing TVET centers to deliver quality training | 5.2.1.1 Strengthen TVET center personnel capabilities to procure equipment and machines through trainings and system development (Procure advanced TVET machines and tools relevant to TVET curricula and repair old machines; Renovate and rehabilitate public TVET institutes). | 80% of functional public Technical institutes have got adequate and relevant equipment and tools for each Course. |  |  |  |  | 0 |  |  | X |  | 300000 |  |  | X |  | 300000 |  |  | X |  | 300000 |  |  | X |  | 300000 | MOEHS, GIZ , NGO consotium
|  | 5.2.2 Adopt highly specialized advanced technical skills for learners | 5.2.1.2 Undertake extensive labor market survey to determine advanced and highly employable skills trainings. | labor market survey completed and used to inform TVET programme design |  |  |  |  | 0 | X |  |  |  | 70000 | X |  |  |  | 0 | X |  |  |  | 0 | X |  |  |  | 0 | MOEHS, GIZ , NGO consotium
| 5.2 | 5.2.3 Enhance the quality and relevance of TVET through training of instructors and center managers | 52.3.1 Establish TVET instructors’ training department TVET/TVQA departments. | TVET departments established and functioning |  |  |  |  | 0 | X |  |  |  | 46600 | X |  |  |  | 21600 | X |  |  |  | 26601 |  |  |  |  | 21602 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.2 Train and produce 200 highly skilled TVET instructors. | 200 TVET instructors trained |  |  |  |  | 0 |  |  |  |  | 100000 |  |  |  |  | 100000 |  |  |  |  | 100000 |  |  |  |  | 100000 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.2 Upgrade capacity of TVET center staff through on-the-job training. | provided with center based TVET job training. |  |  |  |  | 0 |  | X |  |  | 30000 |  |  | X |  | 35000 |  |  |  | X | 40000 |  |  |  |  | 50000 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.3 Register, assess and accredit TVET centers/Institutes | 90% of existing TVET centers/institutes are accredited By TVQA. |  |  |  |  | 0 |  |  |  |  | 30000 |  |  |  |  | 35000 |  |  |  |  | 40000 |  | X |  |  | 50000 | MOEHS, GIZ , NGO consotium
|  | 5.2.4 Improve the relevance and quality of TVET curriculum by adapting and Implementing competency based curriculum | 5.2.3.4 Develop Competence-based Curriculum and implement for all levels. | , 80% of public and private TVET centers/ institutes adapt MOE&HS TVET curricula. |  |  |  |  | 0 |  |  |  | X | 300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.2.3.5 Provide on-the-job training and take study tour to TVET staff of MOE&HS | 90% of TVQA and TVET staff complete planned training | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | MOEHS, GIZ , NGO consotium
Improve Internal and External Efficiency of TVET |  | 5.3.1 Standardize and improve assessment and certification of TVET trainees. | 5.3.1.1 Train public TVET examiners and assessors. | . all TVET examinations are standardized and administered By SLNECB |  |  |  |  | 0 |  | X |  |  | 300000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.1.2 Establish and operationalize TVET examination unit under SLNECB. | all TVET examinations are standardized and administered By SLNECB |  |  |  |  | 0 |  |  | X |  | 10000 |  |  |  | X | 5000 |  |  |  |  | 0 |  |  |  |  | 5000 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.1.3 Strengthen/Develop TVET examination checklist/guideline. | . all TVET examinations are standardized and administered By SLNECB |  |  |  |  | 0 |  |  |  | X | 24000 |  |  |  | X | 24000 |  |  |  | X | 24000 |  |  |  |  | 24000 | MOEHS, GIZ , NGO consotium
| 5.3 | 5.3.2 Prepare TVET graduates for employability in the labor market | 5.3.2.1 Establish employment promotion units at TVET centers. | , unites established and functioning |  |  |  |  | 0 | X | X | X | X | 10000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.2 Collaborate with MOLSA on linkages of TVET graduates to employers for apprenticeships. | workplace linkages fully established |  |  |  |  | 0 |  |  | X | X | 30000 |  |  |  |  | 0 |  |  | X | X | 30000 |  |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.3 Provide business startup capital to 120 TVET graduates. | business capital provided to planned number of trainees |  |  |  |  | 0 |  |  | X | X | 30000 |  |  |  |  | 0 |  |  | X | X | 30000 |  |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.4 Pilot crowdfunding platform in collaboration with MOLSA to enhance availability of funds for business-minded TVET students. | pilot implemented |  |  |  |  | 0 | X |  |  |  | 30000 |  |  |  |  | 0 | X |  |  |  | 30000 |  |  |  |  | 0 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.5 Remuneration/admin for TVET center and MOEHS staff (salary costs). | [5 empty] | 0 | X | X | X | X | 72000 | X | X | X | X | 72000 | X | X | X | X | 72000 | X | X | X | X | 72000 | MOEHS, GIZ , NGO consotium
|  |  | 5.3.2.6 Undertake TVET tracer study | tracer studies completed as planned |  |  |  |  | 0 |  |  |  | X | 1400899.25 |  |  |  | X | 1400899.25 |  |  |  | X | 1400899.25 |  |  |  | X | 1400899.25 | MOEHS, GIZ , NGO consotium
[9 empty] | 0 |  |  |  |  | 7101499.25 |  |  |  |  | 6896499.25 |  |  |  |  | 7476500.25 |  |  |  |  | 4440501.25 | 25915000
HIGHER EDUCATION
Priority objective | Priority Code | Strategies | Activities | Targets |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 | resource /Responsibility
Increase equitable access to higher education in Somaliland |  | 6.1.1 Increase enrolment with an emphasis of girls | 6.1.1.1 Conduct gender needs assessments for intervention | assessments completed and used to shape policy |  |  | X | X | 20000 |  |  | X | X | 20000 |  |  | X | X | 20000 |  |  | X | X | 10000 |  |  | X | X | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
| 6.1 |  | 6.1.1.2 Provide scholarship grants for 200 girls and disadvantaged students | 200 scholarships granted | X | X | X | X | 30000 | X | X | X | X | 60000 | X | X | X | X | 90000 | X | X | X | X | 120000 | X | X | X | X | 150000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.1.1.3 Develop a comprehensive survey of facility expansion needs {higher education minimum standards} | 50% of universities apply gender sensitive minimum standards |  |  |  | X | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 6.2.1 Develop and enforce HE key policy documents and guidelines including quality assurance | 6.2.1.1 Conduct a study on capacity gaps in University human resource | , 50% of lecturers have advanced degrees |  |  |  | X | 0 |  |  | X |  | 120000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
Improve quality and relevance of higher education in Somaliland |  |  | 6.2.1.2 Conduct research and support academic journals | , 5 research papers published |  |  | X |  | 69058.0693 | X |  |  |  | 69058.0693 | X |  |  |  | 69058.0693 | X |  |  |  | 69058.0693 | X |  |  |  | 69058.0693 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.3 Develop M&E framework and do regular monitoring | Degree programmes operational with emphasis on entrepreneurial production in marine resources, livestock By products, agriculture, food processing and solar energy |  |  |  | X | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 |  |  | X |  | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.4 Promote higher education relevance and link with national natural resource, to encourage entrepreneurship | , all 35 Universities publish Annual Reports |  | X |  |  | 100000 |  | X |  |  | 100000 |  | X |  |  | 100000 |  | X |  |  | 100000 |  | X |  |  | 100000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.5 Implement HE minimum standards for all HE institutions | Current situation is reviewed and policy is operational to harmonize curriculum framework | X | X | X | X | 50000 | X | X | X | X | 50000 | X | X | X | X | 50000 | X | X | X | X | 50000 | X | X | X | X | 50000 | EU, UNICEF, MoE&HS, USAID, GPE,
| 6.2 |  | 6.2.1.6 Adopt standard curriculum framework for Higher education and review for relevance and marketability | Policy is developed and made operational to merge universities |  |  | X | X | 90000 | X | X |  |  | 90000 | X | X |  |  | 0 |  | X |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.7 Develop and implement HE policies including merging universities | 3 universities or constituent colleges merged. |  |  |  |  | 0 |  |  | X | X | 150000 | X | X |  |  | 160000 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.2.1.8 Review and prepare a plan for filling the capacity gaps in the University human resource. | Capacity Assessment reports prepared and recommendations implemented. |  |  |  |  | 0 |  |  |  |  | 120000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
Improve internal and external efficiency of HE |  | 6.3.1 Improve capacities of Directorate staff | 6.3.1.1 Build directorate staff capacities | 80% of the university faculty received planned training. |  |  |  |  | 1182941.9307 |  |  | X | X | 1682941.9307 |  |  |  |  | 2182941.9307 |  |  |  |  | 2682941.9307 |  |  |  |  | 3182941.9307 | EU, UNICEF, MoE&HS, USAID, GPE,
| 6.3 |  | 6.3.1.2 Construct and furnish the Commission of Higher Education Centre. | the construction and furnishing of the Office of Commission of completed and building functional | [9 empty] | 50000 | [15 empty] | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 6.3.1.3 Review remuneration structure for lecturers | remuneration structure for lecturers harmonized |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
[9 empty] | 1582000 |  |  |  |  | 2552000 |  |  |  |  | 2712000 |  |  |  |  | 3072000 |  |  |  |  | 3592000 | 13510000
GOVERNANCE
Priority objective | Priority Code | Strategies | Activities | Targets |  |  |  |  | 2017 |  |  |  |  | 2018 |  |  |  |  | 2019 |  |  |  |  | 2020 |  |  |  |  | 2021 | resource /Responsibility
Priority Objective 7.1: Improve and strengthen governance and Capacity development for MOEHS system |  | 7.1.1 Strengthen regulatory environment for the sector | 7.1.1.1 Review and harmonize all existing policies, and operationalize the policies. | 20 , policies , manuals, and guidelines are functional and in place |  |  |  |  | 0 |  |  | X | X | 200000 |  |  | X | X | 300000 |  |  | X | X | 250000 |  |  | X | X | 250000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.1.2 Strengthen organizational capacity of the ministry of education | 7.1.2.1 Develop all Education subsectors manuals and guidelines for management and operations | , all the required manuals are printed, and distributed for use. |  |  |  |  | 0 |  |  | X | X | 100000 |  |  | X | X | 50000 |  |  | X | X | 50000 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.1.3 Strengthen capacity of staff to delivery effective services | 7.1.3.1 Carry out HRD needs assessment and competencies at all levels of the management system (central down to school) | By 2018, needs assessment completed and used to shape capacity development programme |  |  |  |  | 0 |  |  |  |  | 30000 |  |  |  |  | 0 |  |  |  |  | 30000 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.1.3.2 Organize HRM orientation for MOEHS staff | at least 70% of MOEHS staff received HRM information |  |  |  |  | 0 |  |  |  |  | 0 | X | X |  |  | 150000 | X | X |  |  | 100000 |  |  | X | X | 100000 | EU, UNICEF, MoE&HS, USAID, GPE,
| 7.1 |  | 7.1.3.3 Develop long-term, on-going capacity building strategy for staff at all levels based on the capacity gaps assessment report | capacity building strategy operational |  |  |  |  | 0 |  |  |  | X | 294000 | X |  |  |  | 294000 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.1.3.4 Recruit Local and international technical advisors for NFE, planning, teacher training, curriculum, TVET and Quality assurance, and a Chief Technical Advisor for Higher Education. | 70 of HODs management capacity improved |  |  |  |  | 0 |  | X |  |  | 378000 |  |  | X |  | 378000 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | Provide targeted training to upgrade the technical competence of selected staff. | 30 MOEHS Officials acquired technical knowledge |  |  |  |  | 0 |  | X | X |  | 15000 |  | X | X |  | 15000 |  | X | X |  | 15000 |  | X | X |  | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.1.3.5 Remuneration/basic pay for MOEHE staff (salary and allowances). |  | X | X | X | X | 286133.3333 | X | X | X | X | 344689.7185 | X | X | X | X | 403246.1037 | X | X | X | X | 461802.4888 | X | X | X | X | 520358.874 | EU, UNICEF, MoE&HS, USAID, GPE,
Build the institutional capacity of curriculum centre | 7.2 |  | 7.1.3.6 MOEHS admin and recurrent annual costs |  | X | X | X | X | 4612738.5467 | X | X | X | X | 5556722.5693 | X | X | X | X | 6500706.5919 | X | X | X | X | 7444690.6145 | X | X | X | X | 8388674.6371 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.2.1 Upgrade curriculum centre physical facilities and resources | 7.2.1.1.Provide essential equipment's and material for printing facilities. | well equipped curriculum institute in place |  |  |  |  | 0 |  | X | X |  | 400000 | X | X |  |  | 25000 |  |  | X | X | 25000 | X | X |  |  | 25000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.2.1.2 Renovate and expand the curriculum Institute with adequate working space. | Curriculum institute constructed ,fully equipped and functional |  |  |  |  | 0 |  |  | X | X | 375000 |  |  | X | X | 375000 | X | X |  |  | 375000 |  |  | X | X | 375000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.2.2 Increase human resource capacities of the curriculum centre | 7.2.2.1 Recruit and train subject specialists for all education subsectors | all required curriculum specialists Available |  |  |  |  | 0 | X |  |  |  | 140400 | X |  |  |  | 140400 |  | X |  |  | 667520 |  | X |  |  | 140400 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | Recruit a team of subject panelist and curriculum developers to build capacities of the Curriculum Institute. | well equipped curriculum institute in place |  |  |  |  | 0 |  |  | X | X | 400000 | X | X | X | X | 25000 | X | X | X | X | 25000 | X | X | X | X | 25000 | EU, UNICEF, MoE&HS, USAID, GPE,
Establish full functioning of Somaliland National College of education | 7.3 | 7.3.1 Establish the Somaliland National College of Education | 7.3.1.1 Complete and implement SNCE master plan | National teacher training institute constructed ,fully equipped and functional | X | X | X | X | 1000000 | X | X | X | X | 750000 | X | X | X | X | 750000 | X | X | X | X | 750000 | X | X | X | X | 750000 | EU, UNICEF, MoE&HS, USAID, GPE,
Promote and Maintain evidence based EMIS Data for all education subsectors | 7.4 | 7.4.1 Strengthen Education Management Information System (EMIS) | 7.4.1.1 Collect EMIS data on yearly basis for education subsectors (rolling out) | Evidence based EMIS system in place and functional |  | X |  |  | 200000 |  | X |  |  | 210000 |  | X |  |  | 220500 |  | X |  |  | 231525 |  | X |  |  | 243101.25 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.4.1.2 Decentralize the EMIS system including training of education personnel at subnational level | All districts have functioning EMIS systems in place |  |  |  | X | 50000 | X |  |  |  | 90000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.4.1.3 Print and disseminate EMIS report to all subnational education offices | Annually EMIS reports distributed to subnational offices |  |  | X |  | 10000 | X |  |  |  | 10000 | X |  |  |  | 10000 | X |  |  |  | 10000 | X |  |  |  | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.4.1.4 Update school management records | Annually school management records updated |  |  |  |  | 30000 |  |  |  |  | 30000 |  |  |  |  | 30000 |  |  |  |  | 30000 |  |  |  |  | 30000 | EU, UNICEF, MoE&HS, USAID, GPE,
Decentralize primary education functions to the local governments | 7.5 | 7.5.1 Strengthen the policy framework for decentralization of education services | 7.5.1.1 Develop regulatory framework for decentralizing education services | primary education service delivery contribution of Local government increased to 10% |  |  |  |  | 0 |  |  |  | X | 10000 |  |  |  | X | 10000 |  |  |  | X | 10000 |  |  |  | X | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.1.2 Develop framework for local government revenue generation for domestic financing of education services | , a framework for domestic financing of education services is operational. |  |  |  |  | 0 |  |  |  |  | 0 |  |  | X |  | 12000 |  |  | X |  | 12000 |  |  | X |  | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.5.2 Expand education decentralization service delivery for new district councils with JPLG | 7.5.2.1 Select pilot district councils to implement decentralized education functions | , all 14 districts are benefiting from decentralization policy. |  |  |  |  | 0 |  | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 25000 | X | X | X | X | 25000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.2.2 Conduct capacity assessment for district councils | By 2019, capacity assessment completed and used to inform decentralization policy |  |  |  |  | 0 |  |  | X | X | 30000 | X | X |  |  | 30000 | X | X |  |  | 30000 | X | X |  |  | 35000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.2.3 Conduct monitoring and oversight for primary education decentralized functions to the local governments | All district conduct monthly monitoring visits to schools. |  |  |  |  | 0 |  |  |  |  | 10000 |  |  |  |  | 10000 |  |  |  |  | 10000 |  |  |  |  | 10000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.5.2.4 Conduct education sector decentralization coordination meetings | the education sector decentralization coordination meetings |  |  |  |  | 700000 |  |  | X |  | 756000 |  |  | X |  | 816480 |  |  | X |  | 881798.4 |  |  | X |  | 952342.272 | EU, UNICEF, MoE&HS, USAID, GPE,
Implement reliable and effective annual national Examinations. | 7.6 | 7.6.1 Strengthen the capacity of Somaliland National Examination board | 7.6.1.1 Conduct examinations and produce annual reports | By the end of 2021, 100% of learners sit national Examinations and reports disseminated publicly |  |  | X |  | 700000 |  |  | X |  | 756000 |  |  | X |  | 816480 |  |  | X |  | 881798.4 |  |  | X |  | 952342.272 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.1.2 Construct and furnish two Exam setting exam halls, data room for exam center. | By the end of 2021, exam halls will be constructed and fully furnished |  |  |  |  | 0 |  |  | X | X | 80000 | X | X |  |  | 80000 |  |  |  |  | 33000 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.1.3 Construct and furnish eastern regions exam center in Buroa | By the end of 2021, eastern regions Exam centre in Buroa |  |  |  |  | 0 |  |  | X | X | 65000 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.1.4 Conduct country-wide awareness raising on exam cheating and fraud | By the end of 2021, all regions participated in capacity building sessions on fraud and cheating. |  |  |  |  | 0 |  | X | X |  | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | X | X | X | X | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.6.2 Strengthen data management systems of examination board | 7.6.2.1 Update evaluation system so that formative examinations form a component of overall final student learning assessments, rather than relying only on one data point (i.e. final exams) | By the end of 2021, five formative assessment should be conducted |  |  |  |  | 0 |  |  | X | X | 15000 |  |  | X | X | 15000 |  |  | X | X | 15000 |  |  | X | X | 15000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.2.2 Establish Exam Data Bank, permanent subject heads and experts | By the end of 2021, 17 subject experts in place and 1 central Data Bank established. |  |  |  |  | 0 |  |  | X | X | 108000 | X | X |  |  | 108000 | X | X |  |  | 108000 | X | X |  |  | 108000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.6.2.3 Remuneration for MOE&HS exam center technical and management team (staff salary costs). |  |  |  | X | X | 264000 | X | X | X | X | 264000 | X | X | X | X | 264000 | X | X | X | X | 264000 | X | X | X | X | 264000 | EU, UNICEF, MoE&HS, USAID, GPE,
Ensure that children access education in safe and protected learning environments in situations of emergency | 7.7 | 7.7.1 Strengthen resilience of education system to ensure continuation of education services before, during and after the emergencies. | 7.7.1.1 Develop and review education in emergency comprehensive contingency plan including capacity development on school safety | timely response to emergency situations |  |  |  |  | 0 |  |  | X |  | 3000 | X |  |  |  | 3000 | X |  |  |  | 3000 | X |  |  |  | 3000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.2 Conduct rapid education in emergency assessment | timely up to date rapid assessment reports |  |  |  |  | 0 |  |  |  |  | 20000 |  |  |  |  | 20000 |  |  |  |  | 20000 |  |  |  |  | 20000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.3 Provide EIE training for MOE staff at all levels | 200 central, regional and districts MOE and trained |  |  |  |  | 0 | X |  |  |  | 12000 | X |  |  |  | 9000 | X |  |  |  | 8000 | X |  |  |  | 9000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.4 Preposition a package of education supplies for education in emergency | , 50% of education supplies prepositioned to response in high risk areas |  |  |  | X | 800000 | X |  |  |  | 800000 | X |  |  |  | 800000 | X |  |  |  | 800000 | X |  |  |  | 800000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.1.5 Provide contingency funds for EiE | government mobilized and programmes emergency funds |  |  |  | X | 2000000 | X | X | X | X | 2000000 | X | X | X | X | 2000000 | X | X | X | X | 2000000 | X | X | X | X | 2000000 | EU, UNICEF, MoE&HS, USAID, GPE,
|  | 7.7.2 Conduct social mobilization campaign, and establish a coordination mechanism for Education in Emergency. | 7.7.2.1 Establish strong education in emergency coordination system with in ESC, government, and actors. | , EiE is a regular agenda of the coordination meeting at the Ministry of Education | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.2.2 Conduct regular education in emergency coordination meetings with cluster partners. | , 50 national EIE WG meetings held (10 per year over 5 years) | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | X | X | X | X | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
|  |  | 7.7.2.3 Advocate and raise awareness to CEC, Head teachers, and communities | , 75% CECs communities sensitized on EIE management. |  |  | X |  | 0 |  | X |  |  | 0 |  | X |  |  | 0 |  | X |  |  | 0 |  | X |  |  | 0 | EU, UNICEF, MoE&HS, USAID, GPE,
[9 empty] | 10652871.88 |  |  |  |  | 14292812.2878 |  |  |  |  | 14700812.6955 |  |  |  |  | 15587134.9033 |  |  |  |  | 16106219.3051 | 71339851.0717