## ECE Action Plan AA1 (hidden)
Action area 1: Management and Planning |  |  |  |  | Projected Targets
Policy Goal: A Policy environment that supports a well-governed and equitable KG sector |  |  |  | Baseline | 2020 | 2021 | 2022 | 2203 | 2024
Policy Goal Indicator
SN | Activity and (quantity of input) | Sub Activities | Output Indicator | Targets | [5 empty] | Cost Per Year | [9 empty] | Responsible entity | Funding Source | Targets | [5 empty] | Cost Per Year | [6 empty] | Responsible entity | Funding Source
|  |  |  | Baseline / Input | Projected Targets |  |  |  |  | Unit Cost | Unit cost |  |  |  | Projected Cost Per Year | [6 empty] | Baseline | Projected Targets |  |  |  |  | Unit Cost | Baseline | Projected Cost Per Year
[5 empty] | 2020 | 2021 | 2022 | 2203 | 2024 |  | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024 |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Objective 1.1: Strengthen alignment of KG Guidelines with other key documents at global, regional and national level for effective KG delivery
Objective 1.1 Indicator
Strategy 1.1.1: Establish and institutionalize a system for sharing information on protocols, conventions and policies on ECE
Strategy 1.1.1 Indicator
1.1.1.1 | Designate personnel to facilitate the establishment and institutionalization of information-sharing system | 1. Develop terms of reference for personnel. | No. of Personnel Designated | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOE-PT, GES-BED/ECE Unit | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Select the personnel with requisite skills and issue letters of respnsibility. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Agree on timelines of delivery and commission the process | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | MOE-PT, GES-BED/KG Unit
1.1.1.2 | Design a system for information-gathering and sharing (face-to-face, print and electronic) for the entire system starting with ECE | 1. Advertize and contract a firm for the design and development of the information system | An Information sharing system designed, documented and operationalised | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Conduct training for the system managers at all levels | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Launch and operationalize the information system | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Institute timelines for regular information sharing. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1.3 | Develop and implement a communication strategy in line with the ESP to disseminate the relevant guidelines of quality KG in Ghana | 1. Constitute a team to prepare draft communication strategy document/guideline in line with the ESP | A well-documented Communication strategy developed and operationalised | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOE-PT, MOE PR Unit, GES-BED/ECE Unit, GES PR | [14 empty] | MOE-PT, MOE PR Unit, GES-BED/ECE Unit, GES PR
|  | 2. Organize meetings at all levels to present the draft document and take relevant inputs | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | MOE-PT, MOE PR Unit, GES-BED/ECE Unit, GES PR
|  | 3. Finalize and train PR and relevant staff to implement the Communication Strategy | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [15 empty] | MOE-PT, MOE PR Unit, GES-BED/ECE Unit, GES PR
Strategy 1.1.2: Periodic review of KG guidelines to align with international, and national standards and conventions
Strategy 1.1.2 Indicator
1.1.2.1 | Conduct periodic comprehensive review of the KG Policy implementation | 1. Develop a comprehensive KG Policy assessment tool | No. of persons reached with relevant KG guidelines | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MoE PT, GES BED
|  | 2.Train staff on the use of the assessment tool | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Conduct periodic assessment and analyze the results | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Organize Review meetings to discuss the assessment report | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5. Use findings to revise KG policy periodically. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Objective1.2: Ensure coordination of KG policies and programs for both state and non-state actors at national and sub-national levels
Objective1.2 Indicator
Strategy 1.2.1: Establish an inter-sectoral coordinating mechanism for KG programmes delivery at all levels (National, and Sub-national)
Strategy 1.2.1 Indicator
1.2.1.1 | Constitute a Committee of inter-sectoral actors for coordination of KG programs including INSETS (Some Agencies and Divisions' work is linked with KG programms) | 1. Consult various sectors for proposed committee members | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pre-Tertiary MoE, GES, ECE Unit, NIB, NTC, NACCA, NTCE/NAB, Reps. of non-state actors Sub-national: Regional, District, Schools level (RDE, DDE, DD Sup., ECE Coordinators, Planning officer reps of non-state actors, HoS, KG, School Rep., CoHBS)
|  | 2. Develop ToR for the committee's operations | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Orient committee members at national and sub-national levels | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Officially assign and inaugurate the committee | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.2 | Develop a database of key actors (including NGOs, FBO, etc.) and their programmes /plans in the ECE space and ensure roles and responsibilities are clearly defined | 1. Create a database of key KG actors and their programmes | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | National ECE Intra-sectoral Coordinating Committee
|  | 2. Use database to define and document roles and responsibilities. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Upload documentation onto the information system for accessibility | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Conscientize KG actors on their roles and responsibilities | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strategy 1.2.2: Strengthen the capacity of KG policy makers, managers and coordinators for planned programmes at national and sub-national levels
Strategy 1.2.2 Indicator
1.2.2.1 | Orient and train policy makers, managers and coordinators on existing and the new ECE policies and programmes. | 1. Print KG policy documents for distribution natiowide | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MoE - Pre-Tertiary, GES – BED ECE
|  | 2. Organize orientation workshop for Policy makers, managers and coordinators | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Objective 1.3: Ensure adequate and equitable deployment and management of Teachers and other human resource for KG programmes
Objective 1.3 Indicator
Strategy 1.3.1: Ensure efficient deployment of teachers to KG classrooms based on skills, qualification and specialization on
Strategy 1.3.1 Indicator
1.3.1.1 | Conduct an audit of KG-teacher needs nationally to inform deployment and CPD of teachers (training, quota for Study leave) | 1. Develop KG teacher audit tool | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GES HR, NCTE/NAB, NTC, Teacher Education Institutions (CoEs, Universities)
|  | 2. Organize orientation for auditing team | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Conduct a national audit of all KG Teachers | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Analyse the audit findings for further action (e.g. disseminate findings and ensure increase in KG quota for PreSET, study leave and other CPD) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5. Ensure increase quota for ECCD admissions | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1.2 | Ensure adequate deployment of KG teachers nationally | 1. Collate vacancies on KG teachers at national and sub-national levels | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Post/ Repost qualified KG teachers to ensure equity | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Objective1.4: Promote equitable access to KG services, with emphasis on vulnerable populations and children with Special Needs
Objective1.4 Indicator
Strategy1.4.1: Ensure KG facilities are accessible and inclusive for all children
Strategy1.4.1 Indicator
1.4.1.1 | Conduct infrastructural audit based on established guidelines with focus on accessibility and safety of KG facilities | 1. Develop infrastructural audit tool | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EMIS Unit, MOE-FPMU, GES BED
|  | 2. Orient data collectors/audit team on the tool | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EMIS Unit, MOE-FPMU, GES BED
|  | 3. Conduct the infrastructural audit and collate the results for further actions | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EMIS Unit, MOE-FPMU, GES BED
|  | 4. Disseminate findings to inform decision making at all levels. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EMIS Unit, MOE-FPMU, GES BED
Strategy 1.4.2: Ensure the learning needs of all KG children including those with special educational needs are met
Strategy 1.4.2 Indicator
1.4.2.1 | Establish a process to build capacities of classroom teachers and parents/caregivers to identify and manage children with special educational needs | 1. Prepare guidelines for identification and management of children with special needs | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GES-SPED, BED, SHEP, Private schools association
|  | 2. Document the standard process for capacity building of teachers, parants and caregivers | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Review existing practises on CPD for KG teachers on handling children with special educational needs (SEN). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.2.2 | Screen all children before admission into schools to facilitate early detection of special educational needs | 1. Co-ordinate with Ministry of Health/ Ghana Health Service, Ministry of Gender, Children and Social Protection to plan for screening of children | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SHEP, Private schools’ association, Collaborate with GHS
|  | 2. Screen children in all schools prior to admission | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Collate report on children with special educational needs for further action | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.2.3 | Provide appropriate and adequate teaching learning materials for all children and assistive devices for children with special needs | 1. Collate data on TLMs and Assistive Devices (ADs) needed in all schools | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOE/GES Procurement Unit, NACCA, NTC, SPED
|  | 2. Budget for procurement of TLMs and ADs | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Procure and Distribute the TLMs and ADs. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Objective 1.5: Promote evidence informed decision-making at national and sub-national levels
Objective 1.5 Indicator
Strategy 1.5.1: Promote the generation, storage and usage of relevant data for informed decisions at national and sub-national levels
Strategy 1.5.1 Indicator
1.5.1.1 | Conduct research on KG activities to understand the gaps in knowledge and generate evidence for decision making at all levels | 1. Develop terms of reference for the conduct of research on KG activities in Ghana. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SRIM, GES – BED, Collab.: Research and Academic Institutions
|  | 2. Contract a relevant Research Institution to conduct research | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Disseminate research findings | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Use findings to review policy and practices of KG practitioners | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1.2 | Analyse existing data (research) and feed findings into review of KG Policy and major decision making at all levels | 1. Constitute a Teachnical team to analize all existing data at all levels | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MOE SRIM, GES –BED/ECE Unit, Collab.: Research and Academic Institutions
|  | 2. Prepare detailed report for scrutiny | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Use findings to review KG Policy periodically | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Objective 1.6: Develop mechanisms to ensure adequate budgetary allocation for KG programmes at national and subnational
Objective 1.6 Indicator
Strategy 1.6.1:Ensure adequate budgetary allocation (10% of national education budget) to promote KG programmes and activities
Strategy 1.6.1 Indicator
1.6.1.1 | Analyse the current budgetary allocation and advocate for increase to support nationwide implementation of KG programmes | 1. Establish a trend analysis of budgetary allocations | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BED/ECE Unit, Collab.: CSOs- GNECC, GNCRC, NGOs, MMDAs, Pre Tertiary Dept.; MOE
|  | 2. Disseminate findings with key stakeholders | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Use findings to advocate increased budgetary support for KG programmes | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strategy 1.6.2: Reinforce capacity of practitioners to create conducive infrastructure and learning environment for children
Strategy 1.6.2 Indicator
1.6.2.1 | Build capacity of practitioners and KG teachers on implementation of safe school concept (Infrastructure, minimizing or eliminating corporal punishment, sexual harassment, bullying and child abuse) | 1. Organize capacity building workshop for KG teachers and practitionners | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FPMU, PBME) BED/Collab: CENLOS, Teacher Unions, NGOs, CSO, Guidance and Counselling Unit, Parents/community members
|  | 2. Make available safe school concept guidelines (hard/soft copies) to all teachers and practitioners | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Strategy 1.6.3: Institute capacity building support scheme for KG teachers including private school on Play-based learning
Strategy 1.6.3 Indicator
1.6.3.1 | Institute a scholarship and reward schemes for potential and practising practitioners of ECE | 1. Constitute a Scholarship/reward schemes committee | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BED/ECE Unit Collaborators: NGOs, Private schools, Pre Tertiary Dept.; MOE
|  | 2. Develop project proposal and modalities for the schemes | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Identify interested sponsors for the scholarship and reward schemes | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4. Launch the scholarship and reward schemes | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.3.1 | Ensure accreditation of private schools and renewals are tied to staff capacity in play-based pedagogy | 1. Update the accreditation procedures or requirements for KG schools to include play-based pedagogy | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2. Educate the general public and schools on the new accreditation requirements | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3. Enforce implementation of the accreditation requirements | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ECE Action Plan AA2 (hidden)
Area 2: Curriculum Development and Implementation |  |  |  |  | Projected Targets
Policy Goal: Curriculum That Is Implemented to Promote Pre-Primary Children’s Positive (Holistic) Development. Indicator: % of learners demonstrating fundational skills for life and later learning |  |  |  | Baseline | 2020 | 2021 | 2022 | 2203 | 2024
Policy Goal Indicator
SN | Activity and (quantity of input) | Sub Activities | Output Indicator | Targets | [5 empty] | Cost Per Year | [9 empty] | Responsible entity | Funding Source | Targets | [5 empty] | Cost Per Year | [6 empty] | Responsible entity | Funding Source
|  |  |  | Baseline / Input | Projected Targets |  |  |  |  | Unit Cost | Unit cost |  |  |  | Projected Cost Per Year | [6 empty] | Baseline | Projected Targets |  |  |  |  | Unit Cost | Baseline | Projected Cost Per Year
[5 empty] | 2020 | 2021 | 2022 | 2203 | 2024 |  | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024 |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Objective 2.1: Establish a framework to guide participatory development, implementation and review of KG curriculum
Objective 2.1 Indicator
Strategy 2.1.1: Reinforce systems and structures for engaging practitioners (state and non-state) and policy makers on the development, implementation and periodic review of KG curriculum
Strategy 2.1.1 Indicator
2.1.1.1 | Update database of key state and non-state ECE practitioners in the development, implementation and review of curriculum regularly. | Review database of state and non-state ECE practitioners | ECE curriculum aligned to international standards No. of Personnel Designated | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
[11 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
2.1.1.2 | Conduct stakeholder engagements to inform the KG curriculum review. | Conduct wide analysis of ECE curriculum and align it to ESP , MTDP and international standards | Groups of stakeholders engaged in curriculum review process | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, Pre Tertiary Dept.; MOE, National ECE Unit of GES, GES at Regional and District Levels, Teachers
|  | Undertake research on classroom factors to inform KG curriculum review. | Research undertaken to informed curriculum review | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
|  | Engage selected stakeholders in curriculum review process | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.1.1.3 | Coordinate the selection of experts for all KG curriculum development and review. | Coordinate the selection of experts for all KG curriculum development and review | No. of experts and practitioners selected for curriculum development and/or review | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA,
| Sensitise the public on the new (standard- based, 2019) curriculum | Organize community wide sensitization forum in line with Action Area- 4, 4.1.2.4 on new (Standard-based, 2019) KG curriculum | A well-documented Communication strategy developed and operationalised | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
Strategy 2.1.2: Ensure curriculum has culturally relevant supplementary materials for implementation [great to include this—can there be provision for a review process as well as field testing the curric and materials? And is there need to consider local culture and language in materials?
Strategy 2.1.2 Indicator
2.1.2.1 | Develop Teacher Manuals *(reference manuals, resource pack/TLR guides including videos) and other supplementary materials that support differentitated learning | Constitute a technical working Group or experts to write KG supplementary material | Technical working groups constituted | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, IB, BED, NAB
|  | Develop teacher manuals/ resource pack to include differentiated learning in line with the standard -based, 2019 KG curriculum | Culturally relevant materials developed for curriculum implementation | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
|  | Print KG teacher manual and supplementary materials | Teacher manual and supplementarty materials printed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, IB, BED, NAB
| Distribute Teacher Manuals to all KGs across the country | Distribute Teacher Manuals (Soft and hard copies) to all KGs across the country | % of teachers reported receiving relevant resource packs( soft and hard copies) | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.1.2.2 | Build capacity of teachers and other practitioners to implement the curriculum in the areas of: Use of curriculum and supplementary materials, development, use and maintenance of TLRs | Conduct needs analysis of teachers and other practitioners on curriculum implementation | Needs analysis conducted | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, SpED, GES (National, Regional and District Directorates)
|  | Build capacity of teachers and other practitioners on supplementary materials, use and maintenance of teaching and learning resource | Teachers capacity enhanaced on supplementary teaching and learning resource | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, SpED, GES (National, Regional and District Directorates)
| Trialing standard-based 2019 KG curriculum for inputs and feedback incooperated for review | Coordinate the process of trialing standard based 2019 KG curriculum and supplementary materials | KG curriculum and supplementary materials trialed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
|  | Incooperate inputs and feedback from trial for review | KG curriculum and supplementary materials reviewed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
Objective 2.2: Establish equitable implementation of the curriculum to meet grade and context expectations in all KGs
Objective 2.2 Indicator
Strategy 2.2.1: Increase accessibility to the curriculum in varied formats (print, electronic, braille and audio copies)
Strategy 2.2.1 Indicator
2.2.1.1 | Convert the KG Curriculum into multiple formats (e.g. braille, audio and other formats) for users with special educational needs. | Coordinate the translation of KG curriculum into braille, audio and other format. | KG curriculum content in brailled reviewed and scaled up | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, SpED, GES (National, Regional and District Directorates)
|  | Build capacity of teachers on translated braille, audio and other format for special educational needs | Teachers trained on KG curriculum in translated braille, audio and other formats | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.2.1.2 | Distribute KG curriculum to in-service and pre-service teachers and public libraries in right quantities and on time. | Distribute KG curriculum to in-service and pre-service teachers and public libraries in right quantities. | No. of state and non-state Teachers received KG Curriculum | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, PTD, GES (National, Regional and District Directorates)
|  | Provide easy access to KG curriculum for state and non-state practitioners | KG curriculum accessible to state and non-state practitioners | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
Strategy 2.2.2: Standardize assessment at KG and ensure conformity with the KG curriculum( standard-based)- sent to Action area 5 -Monitoring, reporting and quality assurance
Strategy 2.2.2 Indicator
2.2.2.1 | Develop and review standardised assessment tools in line with the Curriculum including that of school readiness assessment | Develop a school readiness assessment tool | School readiness assessment tool developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | NaCCA, Collaborators, MOE, GES-BED, NIB
2.2.2.1 |  | Develop and align standardised assessment tools to the standard-based 2019 curriculum | Stardardized assessment tool developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | NaCCA, Collaborators, MOE, GES-BED, NIB
2.2.2.2 | Distribute assessment tools to all state and non - state KGs across the country in the right quantity and on time | Orient state and non-state KG practitioners on the assessment tools developed | % of state and non-state KG practitioners oriented on assessment tool | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | NaCCA, Collaborators, MOE, NIB, NAB, GES (National, Regional and District Directorates)
2.2.2.2 |  | Distribute assessment tools to all state and non-state KGs across the country in right quantity and on time | % of teachers received assessment tool | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | NaCCA, Collaborators, MOE, NIB, NAB, GES (National, Regional and District Directorates)
|  | Trial assesment tool and scale it up with inputs from the field | Assessment tools trialed and reviewed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.2.2.3 | Build capacity of teachers and supervisors in KG schools (state and non-state) on the use of the assessment tools both for school readiness and school curriculum. |  | Capacity of teachers and supervisors built on the use of assessment tools | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, BED, Regional and District GES
Strategy 2.2.3: Ensure compliance with the minimum guidelines for setting up KGs in Ghana [we agreed this whole strategy and activities will go into AA1]
Strategy 2.2.3 Indicator
2.2.3.1 | Assess existing state and non- state KG Schools (Local, Regional and Central) to identify and fix shortfalls to conform to the minimum standards (infrastructure, class size, learning environment, teachers etc. | Sensitize state and non-state practitioners on the minimum standards for setting up a KG | State and non-state practitioners sensitized on minimum standards | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | NIB-MOE, NAB-MOE, GES
|  | Build capacity of GES management team to support and enforce minimum standards (infrastructure, class size, learning environment, teachers etc. | Capacity of GES Management team built to enforce standards | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.2.3.2 | Distribute and enforce implementation of the minimum guideline for establishing KG that has been developed | Distribute and enforce implementation of the minimum guideline for establishing KG that has been developed | Minimum guidelines distributed to all schools | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | MOE, GES (National, Regional and District Directorate
Objective 2.3: Ensure KG pedagogy is play-based in all Schools
Objective 2.3 Indicator
Strategy 2.3.1: Strengthen the use of inclusive Play-based pedagogy modules for public and private KGs
Strategy 2.3.1 Indicator
2.3.1.1 | Build capacity of teachers (workshop, on-site coaching and mentoring, professional learning community) to enable them integrate play in delivering the KG curriculum | Undertake needs assessment of teachers on the use of play in lesson delivery | Needs assessment on play conducted | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
|  | Build capacity of teachers (Pre- and -In=service ) in the use of play-based learning approaches | Teachers' capacity built on the use of play-based pedagogy | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.3.1.2 | Develop, print and distribute play-based resource pack to all KG schools in the right quantity and on time | Develop KG play-based resource pack to include indigenous play-based activities and differentiated learning strategies | Indigenous play integrated into KG resource pack | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators, MOE, GES-BED, NGOs (Eg. Right To Play, Sabre Education), NC.PECGD
|  | Build capacityof state and non-state practitioners on KG play-based resource pack including indegenous play materials | Teachers' capacity built on the use of indigenous play to deliver curriculum | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
|  | Distribute play-based resource pack including indegenous play materials | No. of Play-based resources packs distributed to KG school Anually | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0
2.3.1.2 |  | Regularly review KG play-based resource pack. | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency; NaCCA; Collaborators, MOE, NIB, NAB, GES, Right to Play, NC.PECGD
Strategy 2.3.2: Develop a roadmap for retooling KGs with play kits
Strategy 2.3.2 Indicator
2.3.2.1 | Conduct needs assessment annually to identify KGs lacking outdoor play equipment |  | Needs assessment on KG outdoor conducted | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency; NIB-MOE, NAB-MOE, GES, NGOs (Eg. Right To Play, Sabre Education), NC.PECGD
2.3.2.2 | Acquire and Install the play equipment for schools. |  | Play equipment for KG installed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency; MOE, Collaborators; MMDAs, NC.PECGD, NGOs (Eg. Right To Play, Sabre Education), PTAs/Communities

## ECE Action Plan AA3 (hidden)
Area 3: Pre-service and Inservice Teacher Education and Training |  |  |  |  | Projected Targets
Policy Goal: Improved skills and competencies of KG teachers on play-based pedagogy |  |  |  | Baseline | 2020 | 2021 | 2022 | 2203 | 2024
Policy Goal Indicator 1 |  | % of teachers using/demonstrating skills in (age appropriate) play-based methodology
Policy Goal Indicator 2 |  | % of teachers using play-based pedagogy in lesson delivery
Policy Goal Indicator 3 |  | % of teachers using age appropriate interactive strategies to organise games for learning
SN | Activity and (quantity of input) | Sub Activities | Output Indicator | Targets | [5 empty] | Cost Per Year | [9 empty] | Responsible entity | Funding Source | Targets | [5 empty] | Cost Per Year | [6 empty] | Responsible entity | Funding Source
|  |  |  | Baseline / Input | Projected Targets |  |  |  |  | Unit Cost | Unit cost |  |  |  | Projected Cost Per Year | [6 empty] | Baseline | Projected Targets |  |  |  |  | Unit Cost | Baseline | Projected Cost Per Year
[5 empty] | 2020 | 2021 | 2022 | 2203 | 2024 |  | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024 |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Objective 3.1: Ensure the training and certification of all KG teachers
Objective 3.1 Indicator |  | % of KG teachers trained and certified
Strategy 3.1.1: Institutionalize the training and certification of all KG teachers to improve quality of teachers
Strategy 3.1.1 Indicator |  | % of KG teachers trained and certified
3.1.1.1 | Draw on existing database on all KG teachers (public and private) to address their training needs (KG pedagogy related to inclusion, qualification and competencies) | 1. Use the NTS and NTEF to develop Assessment Framework to assess KG teachers' competences | Training needs of KG teachers identified | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Conduct need analysis to identify gaps in teachers' competences, pedagogical knowledge and qualifications | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Develop training programmes or tailor existing training programmes to address the identified gaps | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.1.1.2 | Group teachers in zones and develop schedules for training | 1. Classify teachers based on training needs | Training schedules developed for teachers in zonal cohorts | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Further grouping of teachers into zones/districts | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Conduct training programmes to address teachers' needs | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Evaluate the impact of training through administration of questionnaire, interviews and observation of teachers in practice | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.1.1.3 | Organise training for trainers (ToT) | 1. Identify and select trainers | Training for Trainers organised | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Group trainers into zones and develop training schedule | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Conduct training for trainers | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.1.1.4 | Conduct training based on needs analysis and zonal grouping results | 1. Use the Trainer of Trainees to conduct training programmes on zonal levels to address teachers' needs | Zonal Training conducted based on needs assessment results | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Evaluate the impact of training through administration of questionnaire, interviews and observation of teachers in practice ice | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.1.1.5 | Organise training/refresher courses for KG teachers and certify teachers at the end of the training | 1. Use CPD point-base strategy to plan programmes for teachers in line with the current curriculum | Successful participants of refresher training certified | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Develop training schedule in line with CPD Day on the academic calendar | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Organise CPD programmes for teachers and awards points in teacher's logbook | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Award certificate and CPD point to teachers after successful completion of course | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Objective 3.2: Promote the deployment of KG teachers and attendants to areas where they can communicate and teach in the [play] language of the learner.
Objective 3.2 Indicator |  | % of KG teachers and attendants deployed to communities where they can communicate teach in the play language of the learner
Strategy 3.2.1: Ensure compliance with the approved language of instruction /language policy framework for equitable deployment of KG teachers and support staff
Strategy 3.2.1 Indicator |  | % of trained KG teachers and support staff deployed based on approved langauge of instruction/Language Policy
3.2.1.1 | Develop a guideline/criteria to inform the posting of teachers to areas based on their language proficiency | 1. Revise and approve language policy to allow room for use of L1 | Teacher deployment guidelines developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Use sociolinguistic survey to inform teacher deployment | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Map out the predominant language for all KGs/Communities to facilitate effective postings to schools | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Declare teaching vacancies at all levels (national and sub-national) | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 5. Post teachers to fill declared vacancies | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.2.1.2 | Sensitize School leaders and management on the need to recruit attendants who can communicate in the play language of the pupils in their community | 1. Develop a sensitization strategy for school leaders and management on recruitment of KG attendants based on play language of pupils | School leaders and management sensitised on recruitment strategies | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Implement sensitization plan to include community outreach and meeting with school heads and SMCs | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Objective 3.3: Ensure compliance with ECE frameworks for INSET and PRESET
Objective 3.3 Indicator |  | % of Service providers using either INSET and/or PRESET frameworks guidelines for training
Strategy 3.3.1: Strengthen and harmonize existing systems to monitor compliance of Pre-Service and In-Service programmes for effective delivery of ECE
Strategy 3.3.1 Indicator |  | % of Service Providers meeting the standards of the PRESET and INSET delivery
3.3.1.1 | Quality assure training content for PRESET and INSET and ensure that it aligns with the KG curriculum | 1.Conduct Stakeholder engagement to evaluate PRESET and INSET modules and identify the areas of improvement in the content and methodology | PRESET and INSET training contents are quality assured | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Review training modules based on inputs from a wide range of stakeholders | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Use the National Teachers' Standards (NTS)to align contents of the rewiewed PRESET and INSET training Modueles | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Orient PRESET providers and institutions on new PRESET standards | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 5. Map out and orient INSET providers (both public and private) on the new INSET stand | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.3.1.2 | Certify and accredit training modules and facilitators | Liaise with NTC to certify training module award accreditation to facilitators | Training modules certified and facilitators accredited | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.3.1.3 | Develop assessment procedures to monitor implementation of ECE guidelines and impact on teachers’ classroom competencies and children’s learning outcomes for INSET | 1. Use the NTS and NIB inspection tools to develop ECE guidelines for effective monitoring teacher competencies and learners' attainment | Assessment procedures for monitoring of ECEguidelines developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Undertake research aimed at assessing impact of teacher classroom competencies and learning outcomes of pupils | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.3.1.4 | Organise annual INSET and PRESET Review meetings to evaluate progress of implementation for improvement | 1. Engage Service Providers to analyse progress of implementation INSET Programmes and address the gaps that may be identified. | Annual Review meetings conducted | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Meet ECE teacher training institutions to evaluate implementation progress and develop strategies to strengthen it | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 3.3.2: Establish standards for effective delivery of ECE by state and non-state Institutions
Strategy 3.3.2 Indicator |  | Standards for effective delivery of ECE put in place
3.3.2.1 | Set up minimum qualification standards and competency framework for ECE Teacher-educators, teachers and institutions | Set up minimum qualification standards and competency framework for ECE Teacher-educators, teachers and institutions aligned with the current curriculum | Minimum qualification standards and competency framework developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.3.2.2 | Organize training programmes to build the capacity of ECE administrators (Heads of school and proprietors) in school leadership and management | 1. Classify ECE admininistrators based on skill needs | Capacity of ECE administrators built | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Further grouping of the administrators into zones/districts | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Conduct training | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Evaluate the impact of training through administration of questionnaire and interviews | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.3.2.3 | Organise training for KG teachers on conducting Action Research to inform innovation, best practice and decision-making | 1. Group KG teachers into zones/districts | Meeting on action research conducted for KG teachers | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Conduct training through CPD platform and INSET periods | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Assess the impact of training through administration of questionnaire and action research reports of trained teachers | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Objective 3.4: Establish career mechanisms to integrate support staff in KG classrooms
Objective 3.4 Indicator |  | % of support staff integrated into KG classrooms
Strategy 3.4.1: Institutionalize training system for support staff (attendants) in the provision of early childhood education
Strategy 3.4.1 Indicator |  | % of KG support staff trained and integrated into the career path of teachers
3.4.1.1 | Develop modules and schedules for training support staff | 1. Identify qualification requirements for KG assistants/support staff in line with the current curriculum | Modules and Schedules for support staff developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Develop modules in line with curriculum standards | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Develop training schedule | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Undertake the trainings | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.4.1.2 | Organize training (build capacity) for trainers (ToT) | 1. Assess the capacity of TOTs | Training of Trainers workshop organised | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Design training that addresses the gaps | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Undertake the trainings | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.4.1.3 | Develop assessment strategy to monitor progress of trainees | 1. Use the NTS and NIB inspection tools to develop ECE guidelines for effective monitoring teacher competencies and learners' attainment | Assessment strategies to monitor progress of trainees' developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Undertake research aimed at assessing impact of teacher classroom competencies and learning outcomes of pupils | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
3.4.1.4 | Certify qualified candidates (support staff) for selection and placement (upgrade to a specialized KG teacher | 1. Certify qualified support staff | Qualified candidates certified | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Open up application/recruitment process | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Select candidates | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Deploy/Post selected candidates to KGs/schools | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Note on A11: Kingsley-MoE: - Equity and learning outcomes linked but not access - Feasiblity study/Validation workshop - not the root cause but issue of quality - Yes, new KG curriculum, IE inset module, Inset framework for KG teachers, National TLM package for KG as part of delivery KG instruction
Note on A31: Kingsley-MoE: - Linked to access, equity and learning outcomes - Yes, Learning, sociolingustic survey - Yes - Learning, sociolingutic survey \
Note on C37: Kingsley-MoE: Action area 1 factor the posting/deployment of resource person to support special needs kids

## ECE Action Plan AA4 (hidden)
Area 4: Family and Community Engagement |  |  |  |  | Projected Targets
Policy Goal: Families Are Actively Engaged in their Children’s Early Childhood Education |  |  |  | Baseline | 2020 | 2021 | 2022 | 2203 | 2024
Policy Goal Outcome Indicator 1 |  | Increased level of parent participation in KG activities at school
Policy Goal Outcome Indicator 2 |  | Increased parent knowledge about quality ECE
Policy Goal Outcome Indicator 3 |  | Increased parent practice of quality ECE in the home
SN | Activity and (quantity of input) | Sub Activities | Output Indicator | Targets | [5 empty] | Cost Per Year | [9 empty] | Responsible entity | Funding Source | Targets | [5 empty] | Cost Per Year | [6 empty] | Responsible entity | Funding Source
|  |  |  | Baseline / Input | Projected Targets |  |  |  |  | Unit Cost | Unit cost |  |  |  | Projected Cost Per Year | [6 empty] | Baseline | Projected Targets |  |  |  |  | Unit Cost | Baseline | Projected Cost Per Year
[5 empty] | 2020 | 2021 | 2022 | 2203 | 2024 |  | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024 |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Objective 4.1: Develop and implement a systematic guideline for community engagement
Objective 4.1 Indicator
Strategy 4.1.1: Gather evidence on family/ community engagement to develop a comprehensive community engagement strategy
Strategy 4.1.1 Indicator
4.1.1.1 | Identify best practices, evidence and approaches for effective schools-family-community engagement | Do a Situational analysis (desk review) and evidence synthesis on best practices to tease out Key areas of focus for best practices and approaches to effective schools-family-community engagement | No. of best practices reviewed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Organise stakeholder meetings to identify best practices and approaches to schools-family-community engagement | No. of stakeholder meetings | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
4.1.1.2 | Organise a technical working group to develop guidelines for effective school-family-community engagement based on the evidence gathered | Develop a terms of reference to guide the operation of the technical working group to develop guidelines | TOR developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | identify institutions and individual experts to constitute the working group. | Working Group constituted with required institutions/individual experts | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Hold meetings/workshops to develop the guidelines | Guidelines developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Validate the guideline on effective school-family-community engagement | Draft guidelines available for use | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
4.1.1.3 | Roll out the guidelines for effective school-family-community engagement | Pilot the guidelines | Guidelines pilots in XX communities | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Review the guidelines | Revised guidelines | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Prepare to scale up the guidelines | Scale plan developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 4.1.2: Leverage existing structures to promote school-family-community engagement through various platforms
Strategy 4.1.2 Indicator
4.1.2.1 | Engage family and community on their role in promoting quality ECE | Sensitise parents on their role in promoting quality ECE during PTA meetings, school events (Open/Speech and Prize Giving/Graduation Day/community meetings/etc), SPAM meetings, etc. | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Sensitise community leaders/faith-based leaders/other community stakeholders on their role in the guideline that has been developed and actions to support. | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
4.1.2.2 | Deliver capacity building events for parents and community leaders/faith-based leaders/ other community stakeholders on providing ECE in school and at home (i.e. how to play with your child at home, how to prepare your child for school, etc.) | Deliver capacity building to community leaders/faith-based leaders and other community stakeholders | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Deliver capacity building to parents | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Objective 4.2: Strengthen the capacity of ECE practitioners on effective school-family-community engagement on ECE
Objective 4.2 Indicator
Strategy 4.2.3: Develop a training plan based on existing evidence and incorporate into existing in-service training framework
Strategy 4.2.3 Indicator
4.2.3.1 | Organise training of trainers for resource personel on the guidelines for effective school-family-community engagement on ECE | Working Group develops the training materials | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Train resource persons across the levels to facilitate the rollout of the effective school-family-community engagement guideline | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
4.2.3.2 | Organise INSET for Headteachers and KG teachers (state and non-state) on the guideline for effective school-family-community engagement | Deliver INSET for selected Headteachers and KG teachers on guidelines for effective school-family-community engagement | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
4.2.4: Integrate the guidelines on effective school-family-community engagement in pre-service curriculum and course manual
4.2.4 Indicator
4.2.4.1 | Engage Teacher Education Institutions to adopt the guideline for effective school-family-community engagement in ECE teacher education course manual | Hold consultative meeting with Teacher Education Institutions, NCTE and NTC on adoption of the guidelines in the pre-service teacher training and training manual | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Integrate guidelines into pre-service teacher training and teacher training manual | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Objective 4.3: Promote emerging issues through the National Communication Strategy
Objective 4.3 Indicator
Strategy 4.3.1: Sensitise/empower and build capacity of families/community on the need to enrol their children in KG at the Right age and prepare them for transition from home to school, punctuality, retention and completion.
Strategy 4.3.1 Indicator
4.3.1.1 | National mass media campaign on Right Age Enrolment using the C4D strategy | Continue to organize national mass media compaign on Right Age Enrolment using C4D strategy | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Organise community town hall meetings to create awareness on right age enrolment, punctuality, retention and completion. | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Conduct talk shows/commercials/radio dramas on Right Age Enrolment on various media platforms (TV, Radio) | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 4.3.2: Sensitise/empower and build capacity of families/community on the role of parents and communities in providing ECE
Strategy 4.3.2 Indicator
4.3.2.1 | National mass media campaign on the Role of Parents and Communities in providing ECE usingthe C4D strategy | Develop key messages for media campaign | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Organise community town hall meetings to create awareness on the role of parents and communities in providing ECE | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Conduct talk shows/commercials/radio dramas on the role of parents and communities in providing ECE on various media platforms (TV, Radio) | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit

## ECE Action Plan AA5 (hidden)
Area 5: Monitoring, Regulation and Quality Assurance |  |  |  |  | Projected Targets
Policy Goal: Quality Assurance that Improves the Pre-Primary Sub-Sector Through Monitoring, Evaluation, and Research |  |  |  | Baseline | 2020 | 2021 | 2022 | 2203 | 2024
Policy Goal Outcome Indicator 1 |  | Improved KG delivery to support school readiness
Policy Goal Outcome Indicator 2 |  | Annual Education Sector Report published, including KPIs on KG, results from studies and learning assessements to improve school readiness
Policy Goal Outcome Indicator 3 |  | KG delivery aligned to national, regional and international standards
Policy Goal Outcome Indicator 4 |  | ECE platform for sharing information in place
SN | Activity and (quantity of input) | Sub Activities | Output Indicator | Targets | [5 empty] | Cost Per Year | [9 empty] | Responsible entity | Funding Source | Targets | [5 empty] | Cost Per Year | [6 empty] | Responsible entity | Funding Source
|  |  |  | Baseline / Input | Projected Targets |  |  |  |  | Unit Cost | Unit cost |  |  |  | Projected Cost Per Year | [6 empty] | Baseline | Projected Targets |  |  |  |  | Unit Cost | Baseline | Projected Cost Per Year
[5 empty] | 2020 | 2021 | 2022 | 2203 | 2024 |  | 2021 | 2022 | 2023 | 2024 | 2020 | 2021 | 2022 | 2023 | 2024 |  |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 |  | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Objective 5.1: Strengthen MRQA processes to ensure alignment of KG Service delivery with global, regional and national standards.
Objective 5.1 Indicator |  | KG delivery aligned to national, regional and international standards
Strategy 5.1.1: Ensure a functional system for information management on protocols, conventions and policies on ECE is established
Strategy 5.1.1 Indicator |  | ECE platform for sharing information in place
5.1.1.1 | Develop and operationalise guidelines for preparation and monitoring of district and regional education M&E plan | 1. Development of guidelines 2. % of Districts and Regions with M&E plans | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.1.1.2 | Develop and implement a National strategy of accountability framework involving NIB, NaCCA, NTC, GES, DEO, REO, head teachers, curriculum leads, circuit supporters and SMCs for achievement of key performance indicators | Development of national accountability framework | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.1.2 Ensure periodic review of KG programmes and activities to budgetary allocations and national and international financial management principles. | [34 empty] | 0
#VALUE! |  | Budgetary allocation to KG programmes improved
5.1.2.1 | Conduct mid-term assessment of the KG policy and budgetary allocations, based on EMIS and learning assessment | Mid-term assessment conducted | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.1.3 Ensure KG facilities are effectively monitored and evaluated to promote accessibility and inclusivity for all children | [34 empty] | 0
#VALUE! |  | Access to and inclusivity of KG facilities enhanced
5.1.3.1 | Conduct a mapping exercise to ascertain the detailed geographical, resource and learning needs of KG schools and children, including CWDs | Mapping on KG infrastructural needs conducted | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.1.3.2 | Use the Annual School Census to undertake an audit of the status of infrastructural needs of all basic schools (including KG) in the country. | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.1.3.3 | Develop a construction plan based on report of the Annual School census and audit (on the status of school infrastructure) to be updated regularly | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.1.3.4 | Assess the impact of constructing 1,111 new KG blocks (within 3km of communities) across the country | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.1.4 Institutionalise M&E system on the training and certification of all KG teachers | [34 empty] | 0
#VALUE! |  | % of KG teachers trained and certified
5.1.5.1 | Conduct M&E on learning needs of all KG children, including those with SEN, are met. | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Objective 5.2: Ensure efficient system for collecting, analysing and reporting of data to facilitate management decision making on KG service delivery. | [34 empty] | 0
Objective 5.2 Indicator |  | Number and % of management decisions made based on data
Strategy 5.2.1 Establish an inter and intra sectorial monitoring, coordinating and evaluation mechanism for programmes delivered at all levels. | [34 empty] | 0
#VALUE!
5.2.1.1 | Monitor activities of key actors to ensure compliance | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.1.2 | Evaluate and support DEOs and REOs to prepare quarterly and annual performance reports based on M&E plan | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.1.3 | Roll out and expand the use of mobile School Report Card (mSRC) and other real-time data tools to inform school planning and ensure accountability in KGs. | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.1.4 | Improve the coverage of private practitioners in the coverage of EMIS data for management decision | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.2.2 Ensure monitoring and evaluation for efficient deployment of teachers to KG classrooms based on skills, qualification and specialization | [34 empty] | 0
#VALUE!
5.2.2.1 | Evaluate KG Teacher deployment practices to ensure compliance with approved PTR norms and Management Strategy EM 3.1.3 of the MTDP | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.2.2 | Conduct assessment on teacher specialisation and use of child-centred pedagogy at KG to inform CPD needs, using classroom observation | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.2.3 Monitor parental and community involvement in KG delivery | [34 empty] | 0
#VALUE!
5.2.3.1 | Develop a monitoring tool on community participation for circuit supervisors | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.3.2 | Include parental questionnaire/focus group in the learning assessment survey | [9 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.2.4: Promote the generation, storage and usage of relevant data for informed decisions at national and sub-national levels
Strategy 5.2.4 Indicator
5.2.4.1 | Conduct research on KG activities to understand the gaps in knowledge and generate evidence for decision making at all levels | 1. Develop terms of reference for the conduct of research on KG activities in Ghana. | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 2. Contract a relevant Research Institution to conduct research | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 3. Disseminate research findings | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 4. Use findings to review policy and practices of KG practitioners | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | 5. Promote the conduct of external research by dissemination of data and report | [8 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
Strategy 5.2.5: Standardize assessment at KG and ensure conformity with the KG curriculum
Strategy 5.2.5 Indicator
5.2.5.1 | Develop and review standardised assessment tools in line with the Curriculum including that of school readiness assessment | Develop a school readiness assessment tool | School readiness assessment tool developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Develop and align standardised assessment tools to revised curriculum | Stardardized assessment tool developed | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.5.2 | Distribute assessment tools to all state and non - state KGs across the country in the right quantity and on time | Orient state and non-state KG practitioners on the assessment tools developed | % of state and non-state KG practitioners oriented on assessment tool | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Distribute assessment tools to all state and non-state KGs across the country in right quantity and on time | % of teachers received assessment tool | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
|  | Pilot assesment tool and scale it up with inputs from the field | Assessment tools piloted | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
5.2.5.3 | Build capacity of teachers and supervisors in KG schools (state and non-state) on the use of the assessment tools both for school readiness and school curriculum. | Build capacity of teachers and supervisors in KG schools (state and non-state) on the use of the assessment tools both for school readiness and school curriculum. | Capacity of teachers and supervisors built on the use of assessment tools | [7 empty] | Projected Cost Per Year 2020: 0; Projected Cost Per Year 2021: 0; Projected Cost Per Year 2022: 0; Projected Cost Per Year 2023: 0; Projected Cost Per Year 2024: 0 | Lead Agency, NaCCA, Collaborators Pre Tertiary Dept.; MOE, National ECE Unit of GES | [14 empty] | MOE-PT, GES-BED/KG Unit
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Unit Costs
Input |  | Unit | Cost
Printing
| Blackand white printing | Page | 0.2
| Colour | Page | 1.7
Workshops |  |  |  | Workshop cost calculator
In Accra
| Venue | day | 500 | In Accra
| T&T | person | 300 | Number of participants | 1
| accomodation | person.day | 500 | Number of days | 1
| food | person.day | 180 | Total cost | 1580
| additional DSA | person.day | 100
In regions
| Venue | day | 300 | In regions
| T&T | person | 150 | Number of participants | 1
| accomodation | person.day | 200 | Number of days | 1
| food | person.day | 150 | Total cost | 900
| additional DSA | person.day | 100