## Intro
National Department of Education
Papua New Guinea
National Education Plan 2015-19 & Addendum
Action Plan
Quality Learning for All
Planning cycle
Q1 | January | Government accounts open; AOFP operational
February
| March | Q1 Quarterly budget review
Q2 | April | Consultations with sector partners
| May | Draft Annual Operational and Financial Plan
| June | Q2 Quarterly Budget Review; Draft AOFP submission to Department of Finance
Q3 | July | Budget negotiations
| August | Senior Education Officers' Conference
| September | Q3 Quarterly Budget Review
Q4 | October | Draft Division Annual Activity Plans
| November | Joint Education Sector Review; Division Annual Activity Plans finalized
| December | Q4 Quarterly Budget Review. Government accounts close
Focus Areas
1 | Access and Equity
2 | Teachers and Teaching
3 | Learning
4 | Alternate Pathways
5 | Local Management
6 | System Strengthening
Responsible
| TED | Teacher Education Division
| CDD | Curriculum Development Division
| NGO | Non-government organisation
| CEA | Church education agency
| HEI | Higher education institution
| UoG | University of Goroka
| UoT | University of Technology (UNITECH)
| DfCDR | Department for Community Development & Religion
| DHERST | Department for Higher Education, Research, Science and Technology
| STC | Save the Children
| PPD | Policy and Planning Division
| ICTD | ICT Division
| FD | Finance Division
| AD | Audit Division
| RED | Research and Evaluation Division
| HROD | Human Resources and Organisational Development Divison
| TSC | Teaching Service Commission

## FA 1
1 | Focus Area |  | Access and Equity
1.1 | Universal Education
1 | Remove barriers rrstricting access to 13 years of education for children from the age of six
2 | Plan school system to achieve Universal Education
14 | Restructure school system
66 | Encourage increased access to licensed ECE centres
1.3 | School fees
10 | Continue to implement and enhance TFF system
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
1.1.1 | TFF school grants | 10 | 39. Number and % of operational schools that receive TFF. | 39. 100% | Nat | PPD | [8 empty] | 12913.8 | 100 |  | 5905.8 |  | 4700 |  | 2208 | 13219.8 | 106 |  | 5905.8 |  | 5000 |  | 2208
1.1.2 | Plan for 1-6-6 school restructure | 1 |  |  | Prov | PPD | [8 empty] | 0 | [7 empty] | 50 | [5 empty] | 50
1.1.3 | To encourage growth of ECE sector | 66 | Development of ECE policy and guidlelines | Guidelines (Minimum Operating Standards) endorsed | Prov | DfCDR/provinces/CEA | [8 empty] | 200 | [5 empty] | 200 |  | 200 | [5 empty] | 200
1.1.4 | Develop and implement equitable TFF formula using PARI as part of major study | 10 | 12. Difference in Prep to G8 NER between best and worst provinces. 13. Difference in Prep to G8 NER between best and worst districts. | 1.1.4. Formula approved by NEB. 12. 10%. 1. 25%. | Nat | TFF / PPD | [8 empty] | 1500 | 300 |  |  |  | 350 |  | 850 | 1500 | 600 |  |  |  | 700 |  | 200
1.1.5 | Devolve TFF responsibility to provinces | 10 | No. of provinces with responsibiity for TFF | 11 | Prov | TFF | [8 empty] | 650 | 300 |  |  |  | 350 |  |  | 0
1.1.6 | Visit provinces to monitor usage | 44 | See FA 5 School Inspection |  | Prov | TFF | [8 empty] | 0 | [7 empty] | 0
[14 empty] | Total | 15263.8 | 700 | 0 | 5905.8 | 0 | 5400 | 200 | 3058 | 14969.8 | 706 | 0 | 5905.8 | 0 | 5700 | 250 | 2408
1.2 | Infrastructure
3 | Develop and implement national infrastructure design standards for all building projects, to cover
4 | Set up quality assurance system to ensure all buildings meet design standards
5 | Implement the School Infrastructure Partnership Prog
6 | Build classrooms, schools, colleges, etc. to cater for projected student numbers
7 | Develop e-learning and infrastructure adaptation program to provide access to learning through the use or technology any time, anywhere - see strateg 27
8 | Provide water sanitation and hygiene (WASH)
9 | Provide all teachers with reasonable and affordable accommodation
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
1.2.1 | To design and endorse standardised buildings | 3 |  | Building designs endorsed | Nat | PMU | [8 empty] | 600 | 600 | [6 empty] | 0
1.2.2 | To develop infrastructure programs for provinces and districts | 5 |  | Plans endorsed by PEBs | Nat | PMU / Prov / Schools | [8 empty] | 50 | [5 empty] | 50 |  | 0
1.2.3 | To build classrooms to approved standards | 6 | 1. Number of schools operational, by sector. 2. Number of classrooms by sector and type | 1. 13,665 (+22%). 2. 33% inc since 2012 | Prov / Sch | PMU / Prov / Schools | [8 empty] | 521216.7 |  |  | 389160 |  | 131000 | 1000 | 56.7 | 513266.7 | 600 |  | 371660 |  | 139900 | 1050 | 56.7
1.2.4 | To build toilets to approved standards | 8 | 4. Number of functional toilets in schools 5. Toilet:pupi ratio (disaggregated by gender) | 4. 70% increase on 2012. 5. 1:25 females, 1:40 males | Prov / Sch | PMU / Prov / Schools | [8 empty] | 9700 |  |  |  |  | 8750 | 950 |  | 10300 |  |  |  |  | 9300 | 1000
1.2.5 | To build functional water facilities to approved standards | 8 | 6. % of schools with functional water facilities. 7. % of schools with handwashing facilities & running water & soap | 6. 70% of students have access to water facilities. 7. 70% schools | Prov / Sch | PMU / Prov / Schools | [8 empty] | 9750 |  |  |  |  | 8750 | 1000 |  | 10300 |  |  |  |  | 9300 | 1000
1.2.6 | To build libraries to approved standards | 49 | 3. Number and % of schools with libraries | Prim 80%, Secondary 95% | Prov / Sch | PMU / Prov / Schools | [8 empty] | 18500 |  |  |  |  | 17500 | 1000 |  | 19600 |  |  |  |  | 18600 | 1000
1.2.9 | Build houses to approved standards | 9 | 17. % of teachers with housing | 75% | Prov / Sch | Prov / schools | [8 empty] | 8700 |  |  |  |  | 8700 |  |  | 9300 |  |  |  |  | 9300
[14 empty] | Total | 568516.7 | 600 | 0 | 389160 | 0 | 174700 | 4000 | 56.7 | 562766.7 | 600 | 0 | 371660 | 0 | 186400 | 4050 | 56.7
1.4 | Equity
11 | Include awareness of equity in all programs and initiatives and review existing policies
12 | Get out-of-school children into school or learning programs and keep in education those at risk of leaving
13 | Conduct disaster risk reduction and climate change adaption
14 | Restructure school system
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
1.4.1 | To include gender issues in all policy documentation | 11 | Please also refer to FA6 Policy Audit |  | Nat | GES | [8 empty] | 1477.1 | 1435.2 | [5 empty] | 41.9 | 183 | 141.1 | [5 empty] | 41.9
1.4.4 | To develop strategies for OOSC based on OOSC report | 12 |  |  | Nat | PPR | [8 empty] | 0 | [7 empty] | 100 | [5 empty] | 100
1.4.5 | To develop and implement a project for OOSC | 12 | 1.9 Number of Out of School Children | 20% of OOSC will receive education | Nat | PPR | [8 empty] | 0 | [7 empty] | 100 | [5 empty] | 100
1.4.7 | To strengthen awareness of disaster preparedness in schools by implementing Emergency in Education and Disaster Risk Management Policy. | 13 |  |  | Prov | UNESCO | [8 empty] | 315.0402 | [5 empty] | 315.0402 |  | 125.7 | [5 empty] | 125.7
1.4.8 | Special and inclusive education | 31 | Please refer to FA2 |  | Nat | TED
[15 empty] | 1792.1402 | 1435.2 | 0 | 0 | 0 | 0 | 315.0402 | 41.9 | 508.7 | 141.1 | 0 | 0 | 0 | 0 | 325.7 | 41.9
[13 empty] | Summary |  | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
[15 empty] | 585572.6402 | 2735.2 | 0 | 395065.8 | 0 | 180100 | 4515.0402 | 3156.6 | 578245.2 | 1447.1 | 0 | 377565.8 | 0 | 192100 | 4625.7 | 2506.6
Unfunded activities
[7 empty] | Implementation plan | [7 empty] | Budget & source
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | level | Responsible | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
1.2.7 | Endorse standards and ensure existing facilites meet standards |  | Please see FA 5 Inspection |  |  | SD | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Part of another activity
1.2.8 | Develop teacher housing policy |  |  | Housing policy endorsed |  | PMU / PPR | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Does not require funding
1.4.2 | To update Gender Equity in Educaton Policy |  |  | GEEP endorsed |  | GES | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Does not require funding
1.4.3 | Deelop and implement strategies to improve female particpiation in education |  | 1.2 Gender parity index, by level | Elem 1, Prim 0.95, Sec 0.95 |  | GES | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Will lead on from 1.4.2
1.4.6 | To visit schools and provide awareness on issues of GBV and other social issues |  | Please refer to FA5 GCD |  |  | GCD | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Part of another activity

## FA 2
2 | Focus Area |  | Teachers and Teaching
2.1 | Pre-service training
15 | Increase the number of teachers trained, to meet increased student demand, while meeting quality standards
68 | For the Department to divest responsibility for the state run Technical and Teacher Colleges to the DHERST
67 | Develop a cadre of teachers/instructors to staff ECE centres
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
2.1.1 | Primary and elementary pre-service teacher training at 12 TTCs to cater for expected student numbers | 15 | 18. Number of teachers employed | 23,784 elementary teachers & 9635 primary teachers | Nat | TED | [8 empty] | 17623.4 | 415.4 | 15000 |  |  |  |  | 2208 | 17914.6 | 706.6 | 15000 |  |  |  |  | 2208
2.1.2 | Update primary pre-service maths and science courses | 16 | 23. % of pre-service colleges using the SBC National Curriculum Statement, syllabuses and teachers guides. 25. % of pre-service colleges using SBC supplementary materials. | 23. 90%. 25. 90% | Nat | TED/STC | [8 empty] | 1050 | [5 empty] | 1050 |  | 1100 | [5 empty] | 1100 |  | GPE ESPIG Component 2
2.1.3 | Institutionalise the CET program into 8 Teachers Training Colleges in 2018 & Provide mentoring and training for the new CET Lecturers | 15 | 18. Number of teachers employed | 4311 additional elementary teachers | Nat | TED | [8 empty] | 594.5 | 178.7 | [5 empty] | 415.8 | 767.5 | 351.7 | [5 empty] | 415.8
2.1.4 | Secondary and TVET pre-service teacher training | 15 | 18. Number of teachers employed | 2933 secondary teachers; 921 TVET teachers | Nat | DHERST | [8 empty] | 1000 | [5 empty] | 1000 |  | 0
2.1.5 | Train more female science and maths teachers | 15 | 18. Number of teachers employed | 2933 secondary teachers | Nat | DHERST/STC | [8 empty] | 1370 | [5 empty] | 1370 |  | 690 | [5 empty] | 690 |  | GPE ESPIG Component 3 $ or K
2.1.7 | Update and publish National Teacher Qualification Framework | 16 |  | TQF | Nat | TED | [8 empty] | 30 | [5 empty] | 30 |  | 0
2.1.8 | Establish guidelines for ECCE teacher training course content | 67 |  | ECCE Teacher Training Course | Nat | CDD/TED/DfCDR | [8 empty] | 50 | [5 empty] | 50 |  | 0
2.1.9 | Expand pre-service ECCE training | 67 | Number of teachers trained | TBD | Nat | DfCDR/NGOs/CEA | [8 empty] | 220 | [5 empty] | 220 |  | 0 | [7 empty] | DFAT PPF (3 provinces); pre-service also at UoG
2.1.11 | Emoluments and goods & services PS Ted | [13 empty] | 8205 | 8205 | [6 empty] | 8205 | 8205
2.1.12 | Emoluments and goods & services TEDElem Tr Ed | [13 empty] | 4944.1 | 4944.1 | [6 empty] | 4944.1 | 4944.1
2.1.13 | Emoluments and goods & services DHERST | [13 empty] | 0 | [7 empty] | 0
[14 empty] | Total | 35087 | 13743.2 | 15000 | 0 | 0 | 0 | 3720 | 2623.8 | 33621.2 | 14207.4 | 15000 | 0 | 0 | 0 | 1790 | 2623.8
2.2 | In-service training
16 | Improve quality of all teachers by implementing a National Teachers’ Competency Framework |  |  | 7735.9 |  | 970
17 | Enhance teacher quality by providing support and professional learning |  |  | 3610.7 |  | 140
18 | Provide specialist training |  |  | 4777.1 |  | 167
19 | Train and support teachers for SBC
20 | Improve management of libraries and records
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
2.2.1 | Publish and distribute the National Teachers' Standards Policy (National Teachers' Competency Framework) | 16 |  | National Teachers' Standards Policy | Nat | TED | [8 empty] | 20 | [5 empty] | 20 |  | 0
2.2.3 | In-service training in elementary SBC | 19 | 15. % of teachers accessing in-service training | 90% | Nat | TED/Provinces/NGOs | [8 empty] | 12672.2 | 55 |  |  |  |  | 12100 | 517.2 | 12717.4 | 100.2 |  |  |  |  | 12100 | 517.2 | DFAT PPF (10 provinces)
2.2.4 | In-service training in primary SBC | 19 | 15. % of teachers accessing in-service training | 90% | Nat | CDD/TED | [8 empty] | 4155 | 55 |  |  |  |  | 4100 |  | 4199 | 99 |  |  |  |  | 4100
2.2.5 | In-service training in primary maths and science | 17 | 15. % of teachers accessing in-service training | 90% | Nat | TED/STC | [8 empty] | 2356 | 56 |  |  |  |  | 2300 |  | 2399 | 99 |  |  |  |  | 2300 |  | GPE ESPIG Component 1
2.2.6 | NIST/PIST | 17 | 15. % of teachers accessing in-service training | 90% | Prov | Provinces | [8 empty] | 8000 |  |  | 8000 |  |  |  |  | 8000 |  |  | 8000
2.2.7 | Special Maths & Science Program | 18 |  |  | Nat | TED/UoT | [8 empty] | 3831 | 131 |  |  |  |  | 3700 |  | 3896 | 196 |  |  |  |  | 3700
2.2.9 | School Libraries In-service Program | 20 |  |  | Nat | TED/OLA | TBD | [7 empty] | 384.075 | 384.075 | [6 empty] | 412.225 | 412.225
2.2.10 | Teacher Qualification Upgrading Program | 17 | 14. # & % of teachers with minimum teaching qualification | Primary 82% diploma; Secondary 72% degree; TVET 85% diploma | Nat | TED/HEIs | [8 empty] | 384.075 | 384.075 | [6 empty] | 412.225 | 412.225
2.2.11 | Emoluments and goods & services IS Ted | [13 empty] | 4754.7 | 4754.7 | [6 empty] | 4754.7 | 4754.7
[14 empty] | Total | 36557.05 | 5819.85 | 0 | 8000 | 0 | 0 | 22220 | 517.2 | 36790.55 | 6073.35 | 0 | 8000 | 0 | 0 | 22200 | 517.2
2.3 | Inclusive Education
31 | Increase awareness of need to inlude children with special needs in mainstream classes where appropriate
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
2.3.1 | Operations of Inclusive Education Resource Centres (formally SERCs) and outreach | 31 | 11. Number and % of special needs students in mainstream education registered with IERC/SERC | 75% | Nat | TED | [8 empty] | 98 | 98 | [6 empty] | 196.4 | 196.4
2.3.2 | To prepare teachers to teach children with special needs | 31 |  |  | Nat | [9 empty] | 1086.5 | [5 empty] | 920 | 166.5 | 766.5 | [5 empty] | 600 | 166.5 | UNICEF plus DFAT
2.3.3 | Emoluments and goods & services Inclusive Education | [13 empty] | 2816.4 | 2816.4 | [6 empty] | 2816.4 | 2816.4
[14 empty] | Total | 4000.9 | 2914.4 | 0 | 0 | 0 | 0 | 920 | 166.5 | 3779.3 | 3012.8 | 0 | 0 | 0 | 0 | 600 | 166.5
[12 empty] | Summary |  |  | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
[15 empty] | 75644.95 | 22477.45 | 15000 | 8000 | 0 | 0 | 26860 | 3307.5 | 74191.05 | 23293.55 | 15000 | 8000 | 0 | 0 | 24590 | 3307.5
Unfunded activities
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | level | Responsible
2.1.6 | Develop and publish Teacher Development Plan, including projections |  |  | TDP |  | TED | [8 empty] | 0 | [7 empty] | 0
2.1.10 | Transfer of TTC staff and budget activities to DHERST |  |  |  |  | TED/DHERST | [8 empty] | 0 | [7 empty] | 0
2.2.2 | Update teacher in-service training needs analysis & Teacher Professional development Plan |  |  | Teacher Professional Development Plan |  | TED | [8 empty] | 0 | [7 empty] | 0
2.2.8 | E-learning In-service Program |  |  |  |  | TED/ICT | TBD | [7 empty] | 0 | [7 empty] | 0

## FA 3
3 | Focus Area |  | Teachers and Teaching
3.1 | Curriculum
21 | Develop and implement curriculum, strengthening STEM curriculum and incorporating gender sensitivity and learning capacity for all levels
22 | Set up SBC quality assurance system, providing curriculum feedback to inform revisions
23 | Produce supplementary SBC learning materials, including teacher and student resource books for all grades
24 | Develop a clear direction for excellence in schools and National High Schools
25 | Ensure TVET programs use approved curriculum and are aligned to industry standards and needs
26 | Provide curriculum in the social and emotional domain (character and values /civics and ethics education) with emphasis on social and community values, cooperation, problem solving, self discipline and critical thinking
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
3.1.1 | Develop SBC Syllabuses and Teacher Guides and Teacher Training Manuals for Senior Primary Schools | 21 | 22. % of schools at each level using the SBC National Curriculum Statement, syllabuses and teachers guides | 100% | Nat | CDD | [8 empty] | 8322.6 | 85 |  |  |  |  | 7700 | 537.6 | 8343 | 105.4 |  |  |  |  | 7700 | 537.6
3.1.2 | Develop SBC Syllabuses and Teacher Guides and Teacher Training Manuals for Junior Secondary Schools | 21 | 22. % of schools at each level using the SBC National Curriculum Statement, syllabuses and teachers guides | 100% | Nat | CDD | [8 empty] | 85 | 85 | [6 empty] | 105.4 | 105.4
3.1.3 | Conduct TOT and Cluster training workshops for Senior Primary and Junior Secondary Schools in all 22 provinces across the country to help teachers teach SBC | 21 | 19. % of teachers reporting use of approved SBC | 90% | Nat | CDD/TED | [8 empty] | 1000 | 1000 | [6 empty] | 1000 | 1000 | [6 empty] | GPE ESPIG Component 2
3.1.4 | Printing, Procurement and distribution of Elementary, Primary & Secondary Standard Based Syllabuses & Teachers Guides & Text books | 23 | 20. % of schools adequately resourced with SBC materials. 21. % of teachers reporting satisfactory access to SBC learning materials | 20. 90% (elem, prim) 50% (sec) 21. 90% (elem, prim) 50% (sec) | Nat | CDD | [8 empty] | 252071.7 | 9964.5 |  | 53151.9 |  | 174672 | 500 | 13783.3 | 265229.7 | 11312.8 |  | 53151.9 |  | 186482 | 500 | 13783
3.1.5 | Printing and distribution of junior primary textbooks for Maths and Science | 23 | 20. % of schools adequately resourced with SBC materials. 24. % of schools at each level using SBC learning materials. 26. Pupil:SBC textbook ratio. | 20. 90% (elem, prim) 50% (sec) 24. 90% (elem, prim) 50% (sec) 26. 1:1 (elem, prim) 3:1 (sec) | Nat | CDD/SCA/JICA | [8 empty] | 21500 | [5 empty] | 21500 | [7 empty] | 21500
3.1.6 | Printing and distribution of elementary maths textbooks | 23 | 20. % of schools adequately resourced with SBC materials. 24. % of schools at each level using SBC learning materials. 26. Pupil:SBC textbook ratio. | 20. 90% 24. 90% 26. 1:1 | Nat | CDD/SCA/JICA | [8 empty] | 7166.6667 | [5 empty] | 7166.6667 | [7 empty] | 7166.6667
3.1.7 | Liaise with TVETD to develop curriculum for TVET courses in secondary schools | 25 |  |  | Nat | CDD / TVETD | [8 empty] | 2000 | [5 empty] | 2000 |  | 2000 | [5 empty] | 2000
3.1.8 | Emoluments and goods & services CDA | [13 empty] | 1471.4 | 1471.4 | [6 empty] | 1471.4 | 1471.4
3.1.9 | Emoluments and goods & services CPD | [13 empty] | 282.5 | 282.5 | [6 empty] | 282.5 | 282.5
3.1.10 | Emoluments and goods & services CDM | [13 empty] | 8965.5 | 8965.5 | [6 empty] | 8965.5 | 8965.5
[14 empty] | Total | 302865.3667 | 21853.9 | 0 | 53151.9 | 0 | 174672 | 38866.6667 | 14320.9 | 287397.5 | 23243 | 0 | 53151.9 | 0 | 186482 | 38866.6667 | 14320.6
3.2 | E learning
27 | Implement e-learning suitable for Papua New Guinea
28 | Use ICT to enhance teaching and learning
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
3.2.1 | Development of e-Learning Policy, Planning Framework and Infrastructure Plan | 28 |  | E learning plan | Nat | ELD | [8 empty] | 170.9 | 170.9 | [6 empty] | 224.7 | 224.7
3.2.2 | Broadcast and roll out EQUITV program | 27 | % of schools using EQUITV |  | Nat | ELD | [8 empty] | 150 | [5 empty] | 150 |  | 155.7 | [5 empty] | 155.7
3.2.3 | To develop e-Learning content | 28 |  |  | Nat | ELD / UNESCO | [8 empty] | 155 | [5 empty] | 155 |  | 150 | [5 empty] | 150 |  | DFAT PPF (10 provinces)
3.2.4 | To upload content to web site | 27 |  |  | Nat | ELD / ICT | [8 empty] | 10 | [5 empty] | 10 |  | 20 | [5 empty] | 20
3.2.5 | e-Learning ON AIR SCHOOL BROADCAST PROGRAMS | 27 |  |  | Nat | ELD | [8 empty] | 0 | [7 empty] | 2.3 | [5 empty] | 2.3 |  | GPE ESPIG Component 1
3.2.6 | Emoluments and goods & services ELD | [13 empty] | 625.5 | 625.5 | [6 empty] | 625.5 | 625.5
[14 empty] | Tot | 1111.4 | 796.4 | 0 | 0 | 0 | 0 | 315 | 0 | 1178.2 | 850.2 | 0 | 0 | 0 | 0 | 328 | 0
3.3 | Early Childhood
29 | Ensure first year of school (preparatory) as an early-childhood education approach, as a transition from home, providing socialisation and foundation literacy and numeracy in readiness for primary school
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | Prov | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
3.3.1 | Work with DfCDR in development of guidelines for establishment of ECCE institutions | 29 |  | Guidelines (Minimum Operating Standards) endorsed | Nat | CDD / PPR / DfCDR | [8 empty] | 1500 | [5 empty] | 1500 |  | 1450 | [5 empty] | 1450 |  | UNESCO plus DFAT
3.3.2 | Work with DfCDR to consult, update and distribute ECE Policy documentation | 29 | 8. ECCE Policy | ECCE Policy endorsed | Nat | CDD / PPR / DfCDR | [8 empty] | 1500 | [5 empty] | 1500 |  | 1450 | [5 empty] | 1450 |  | UNESCO plus DFAT
3.3.3 | Liaise with DfCDR in development and distribution of ECCE curriculum | 29 |  | Curriculum endorsed | Nat | CDD / DfCDR | [8 empty] | 1500 | [5 empty] | 1500 |  | 1450 | [5 empty] | 1450 |  | DFAT PPF (10 provinces)
3.3.4 | Emoluments and goods & services DfCDR |  | Share of DfCDR for ECCE | [11 empty] | 22.4 |  |  |  | 22.4 |  |  |  | 23.9 |  |  |  | 23.9
[14 empty] | Total | 4522.4 | 0 | 0 | 0 | 22.4 | 0 | 4500 | 0 | 4373.9 | 0 | 0 | 0 | 23.9 | 0 | 4350 | 0
3.4 | Assessment
30 | Establish a sustainable national learning assessment system
31 | Increase awareness of need to include children with special needs in mainstream classes where appropriate
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable |  | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
3.3.1 | National Examinations & Certificates Printing and distribution for Grades 8, 10 & 12 | 30 | 28. Students receiving Grade 8 and Grade 10 certificates of education | 100% |  | MSD | [8 empty] | 23912.8 | 14200 |  |  |  |  | 600 | 9112.8 | 23873.8 | 14161 |  |  |  |  | 600 | 9112.8
3.3.2 | Workshops for exam writers, PESs, WEX coords | 30 |  |  |  | MSD | [8 empty] | 500 | 500 | [6 empty] | 500 | 500
3.3.3 | National Exams Marking for 10 WEX and 12 Objectives | 30 |  |  |  | MSD | [8 empty] | 300 | 300 | [6 empty] | 300 | 300
3.3.4 | Assessment workshops for schools | 30 | 27. % of schools using assessment for learning system | 100% |  | MSD / Prov | [8 empty] | 250 | 250 | [6 empty] | 300 | 300
3.3.5 | Capacity building - staff training and competency improvement | 30 |  |  |  | MSD | [8 empty] | 50 | 50 | [6 empty] | 0
3.3.6 | Education bench marking - PILNA & CSMT national student assessment | 30 | 2.1 % of students reaching satisfactory regional literacy and numeracy benchmarks. 2.2 % of students reaching national literacy and numeracy standards | 2.1 Num 55%, Reading 65%, Writing 25%. 2.2 20% increase from baseline |  | MSD | [8 empty] | 400 | 400 | [6 empty] | 400 | 400
3.3.7 | Development of a grade three assessment test to fill the evidence gap on the impact of quality initiatives on early learning | 30 | Literacy and numeracy progress benchmarked |  |  | MSD / CDD | [8 empty] | 200 | 200 | [6 empty] | 200 | 200
3.3.8 | Emoluments and goods & services MSD |  |  |  |  | MSD | [8 empty] | 3036 | 2736 |  |  |  |  | 300 |  | 2736 | 2736
[14 empty] | Total | 28648.8 | 18636 | 0 | 0 | 0 | 0 | 900 | 9112.8 | 28309.8 | 18597 | 0 | 0 | 0 | 0 | 600 | 9112.8
1965
[6 empty] | Summary | [6 empty] | Summary
[15 empty] | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
[15 empty] | 337147.9667 | 41286.3 | 0 | 53151.9 | 22.4 | 174672 | 44581.6667 | 23433.7 | 321259.4 | 42690.2 | 0 | 53151.9 | 23.9 | 186482 | 44144.6667 | 23433.4

## FA 4
4 | Focus Area |  | Alternate pathways
4.1 | Technical and Vocational Education and Training (TVET
32 | . Develop and promote an understanding among parents and students of TVET educational pathways, purpose and routes to employment
33 | Develop TVET as a viable pathway from the mainstream education system for any student from grade 9 onwards (vocational studies in schools and/or dedicated vocational schools)
34 | Introduce a regulatory framework for TVET by passing a Skills Training Act
35 | Deliver all TVET under the National Qualifications Framework using nationally certified courses
36 | Register institutions which deliver TVET certificate courses and meet quality and industry standards
37 | Ensure TVET is seen as flexible and open to all students, providing technical and vocational/job skills
38 | Successful completion of nationally recognised and accredited TVET certificate (II) provides entry into post-secondary TVET certificate (III) and beyond
39 | Support provinces to plan for increased TVET provision, to meet local need
68 | For the Department to divest responsibility for the state run Technical and Teacher Colleges to the DHERST
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
4.1.1 | To actively participate in meetings and conferences to provide awareness campaigns at educational institutions. | 32 | 29. Number of students enrolled in vocational programmes by gender | Male 31,650 Female 21,100 | Prov | TVET oper | [8 empty] | 208.508 | 145.5 |  |  |  |  | 63.008 |  | 166.54 | 101.4 |  |  |  |  | 65.14
4.1.2 | To carry out inspections for TVET teachers, Managers, Infrastructures and tools and Equipment at National and Provincial Institutions. | 36 | 42. % of schools inspected at least once annually | 90% | Prov | TVET Insp | [8 empty] | 332.8 | 127.7 | [5 empty] | 205.1 | 405.6 | 200.5 | [5 empty] | 205.1
4.1.3 | To administer the operations of the state Technical colleges | 33 | 31. Number of vocational, secondary schools, polytechnics, non-trade and trade flexible open-learning institutions operational | 1 VC per district 1 Tech or Bus college per province 1 polytechnic per region | Nat | TVET oper | [8 empty] | 27544.3 | 14513.3 | 12000 |  |  |  |  | 1031 | 40525.6 | 15494.6 | 12000 |  |  |  | 12000 | 1031
4.1.4 | To design and Implement the National Certificates , Technical Training Certificate, Diploma and National Diploma courses Training Packages, Assessement Instruments Resources, tools and Equipment in various TVET Institutions in CBT&A Delivery Mode | 38 | 42 |  | Nat | TVET Curr | [8 empty] | 22098.2 | 317.2 | 10000 |  |  |  | 11000 | 781 | 23177.6 | 396.6 | 10000 |  |  |  | 12000 | 781
4.1.5 | To coordinate and operatate the TVET system | 39 | 29. Number of students enrolled in vocational programmes by gender | Male 31,650 Female 21,100 | Nat | TVET Oper | [8 empty] | 1837 | 1536.1 | [5 empty] | 300.9 | 1930.9 | 1630 | [5 empty] | 300.9
4.1.6 | To design and develop VCD curriculum | 33 |  |  | Nat | TVET curr | [8 empty] | 3137.75 | 1137.75 |  |  |  |  | 2000 |  | 3216.8 | 1216.8 |  |  |  |  | 2000
4.1.7 | To conduct provincial TVET coordinators conference to appraise and strategize provincial TVET development update and needs. | 39 |  |  | Prov | [9 empty] | 2078.6 | 78.6 |  | 2000 |  |  |  |  | 2096.95 | 96.95 |  | 2000
4.1.8 | To review current Provincial TVET Plans to meet provincial demands based on National TVET policies & strategies. | 39 |  |  | Prov | [9 empty] | 78.6 | 78.6 | [6 empty] | 96.95 | 96.95
4.1.9 | To administer HRDPII - construction, teacher training and curr. development | 39 |  |  | Nat | [9 empty] | 16920 | [5 empty] | 16920 |  | 16920 | [5 empty] | 16920
4.1.10 | To divest responsibiity for the Tech and Teachers Colleges to DHERST | 68 |  |  | Nat | [9 empty] | 304 |  |  |  | 304 |  |  |  | 324.5 |  |  |  | 324.5
4.1.11 | Emoluments and goods & services TVET curr | [13 empty] | 2037 | 2037 | [6 empty] | 2037 | 2037
4.1.12 | Emoluments and goods & services voc coord | [13 empty] | 385.7 | 385.7 | [6 empty] | 385.7 | 385.7
4.1.13 | Emoluments and goods & services TVET insp | [13 empty] | 949 | 949 | [6 empty] | 949 | 949
4.1.14 | Emoluments and goods & services TVET coord | [13 empty] | 847.7 | 847.7 | [6 empty] | 847.7 | 847.7
[14 empty] | Total | 78759.158 | 22154.15 | 22000 | 2000 | 304 | 0 | 29983.008 | 2318 | 93080.84 | 23453.2 | 22000 | 2000 | 324.5 | 0 | 42985.14 | 2318
4.2 | Flexible Open and Distance Educatioon (FODE)
40 | Strengthen system of FODE and links between FODE, traditional schooling and TVET to provide viable options for student movement between systems
41 | Promote public awareness of FODE as an option for study outside conventional schools | [29 empty] | 4.6363 | 4.8308
[31 empty] | 4636.3 | 4830.8 | 4323.8 | 4261.8
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
4.2.1 | To adminster FODE / NHS | 40 | 30. Number of FODE enrolments by gender | Male 7750 Female 9150 | Nat | GES | [8 empty] | 575.8 | 312.5 | [5 empty] | 263.3 | 832.3 | 569 | [5 empty] | 263.3
4.2.2 | To print and freight study materials to provinces | 40 |  |  | Nat | FODE | [8 empty] | 3740.9 | 2861.6 | [5 empty] | 879.3 | 3934.3 | 3055 | [5 empty] | 879.3
4.2.3 | To facilitate support Grants to 22 FODE Provincial Centres | 40 |  |  | Nat | FODE | [8 empty] | 50 | 50 | [6 empty] | 50 | 50
4.2.4 | To administer FODE project | 41 |  |  | Nat | FODE / GES | [8 empty] | 1000 |  | 1000 | [5 empty] | 0
4.2.5 | NHS operations | 24 |  |  | Nat | GES | [8 empty] | 1000 | 1000 | [6 empty] | 1000 | 1000
4.2.6 | Emoluments and goods & services FODE |  |  |  |  | FODE | [8 empty] | 2655.3 | 2655.3 | [6 empty] | 2655.3 | 2655.3
4.2.7 | Emoluments and goods & services NHS |  |  |  |  | GES | [8 empty] | 5710.3 | 5710.3 | [6 empty] | 5710.3 | 5710.3
4.2.8 | Emoluments and goods & services FODE NHS operations |  |  |  |  | GES | [8 empty] | 677.2 | 677.2 | [6 empty] | 677.2 | 677.2
[14 empty] | Total | 15409.5 | 13266.9 | 1000 | 0 | 0 | 0 | 0 | 1142.6 | 14859.4 | 13716.8 | 0 | 0 | 0 | 0 | 0 | 1142.6
4.3 | Community Programs
42 | Run National Literacy Program
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
4.3.1 | To review and revise the National Literacy Policy | 42 |  | NLP endorsed | Nat | OLA | [8 empty] | 562.7 | 562.7 | [6 empty] | 607.5 | 607.5
4.3.2 | To establish the National Literacy and Awareness Council (NLAC) | 42 |  |  | Nat | OLA | [8 empty] | 50 | 50 | [6 empty] | 50 | 50
4.3.3 | To monitor and Assess Literacy Program Providers | 42 |  |  | Nat | OLA | [8 empty] | 50 | 50 | [6 empty] | 50 | 50
4.3.4 | Emoluments and goods & services OLA |  |  |  |  | OLA | [8 empty] | 662.7 | 662.7 | 0 | 0 | 0 | 0 | 0 | 0 | 707.5 | 707.5 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Summary |  |  | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
[15 empty] | 94831.358 | 36083.75 | 23000 | 2000 | 304 | 0 | 29983.008 | 3460.6 | 108647.74 | 37877.5 | 22000 | 2000 | 324.5 | 0 | 42985.14 | 3460.6

## FA 5
5 | Focus Area |  | Local management
5.1 | School leadership
43 | Build leadership in schools
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
5.1.1 | Implement the National School Leadership Competency Framework through leadership training for current and future headteachers | 43 | 32. % of principals with training, inclusive of financial management training & 41. NSLC published | 32. 100% & 41. NSCL | Nat | TED/SD | [8 empty] | 3030 | [5 empty] | 3030 |  | 2900 | [5 empty] | 2900
[14 empty] | Total | 3030 | 0 | 0 | 0 | 0 | 0 | 3030 | 0 | 2900 | 0 | 0 | 0 | 0 | 0 | 2900
5.2 | School planning and management
44 | Improve financial management of education institutions
45 | Develop and implement School Learning Improvement Plans | [29 empty] | 4.6363 | 4.8308
46 | Improve standard of school operation and management
47 | Strengthen and support behaviour management systems in schools
48 | Improve community and stakeholder participation
49 | Build and maintain school libraries and manage locally
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
5.2.1 | Financial management training for headteachers and school boards | 44 | 3.4 % of schools using accounting system or combined cash book; 3.5 % of schools submitting acquittals & 3.3 % of schools spending TFF on approved items | 3.4. 90% 3.5 TBD 3.3 90% | Prov | TED/SD | [8 empty] | 100 | [5 empty] | 100 |  | 100 | [5 empty] | 100
5.2.2 | Publish National Quality Schools Standards Framework | 44 |  | NQSSF | Nat | PPD/SD | [8 empty] | 20 | [5 empty] | 20 |  | 0
5.2.3 | Carry out 1 x visit to each school and conduct quality whole school assesment and report to relevant authorities | 46 | 42. % of schools inspected at least once annually. 38. National Quality School Standard Index. | 42. 90%. 38. 20% increase. | Prov | SD | [8 empty] | 13672.7 | 328.7 |  | 8000 |  |  |  | 5344 | 13983.6 | 639.6 |  | 8000 |  |  |  | 5344
5.2.4 | Support schools to develop and implement SLIPs | 45 | 35. % of schools with SLIPs | 100% | School | SD | [8 empty] | 114399.7 | 99.7 |  |  |  | 114100 | 200 |  | 121977.4 | 177.4 |  |  |  | 121800
5.2.5 | Conduct teacher appraisals and Ratings Conferences | 46 | 16. % of teachers meeting minimum teacher standards by level. 1.10 Number and % of teachers meeting national performance standards | 16. 25% increase. 1.10. 25% increase | Prov | SD | [8 empty] | 100 | 100 | [6 empty] | 100 | 100
5.2.6 | Training for inspectors | 46 |  |  | Prov | SD | [8 empty] | 50 | 50 | [6 empty] | 50 | 50
5.2.7 | Support schools to implement the National Behaviour Management Policy & educational guidance | 47 |  |  | Prov | GCD | [8 empty] | 25381 | 81 |  | 2000 |  | 23300 |  |  | 26994.7 | 94.7 |  | 2000 |  | 24900
5.2.8 | To enhance school operation and management | 46 | 33. % of schools with governance board. 34. % of school governance meetings held | 33. 90%. 34. 90% | Prov | SD/Provinces | [8 empty] | 67500 |  |  |  |  | 67500 | [7 empty] | 72100
5.2.9 | To enhance provincal administration and planning |  |  |  | Prov | PPD | [8 empty] | 28200 |  |  | 28200 | [7 empty] | 23200
5.2.10 | Establish a school-based counsellor in every school | 47 | School/SBC ratio | 2 to 1 (sec) | Prov | GCD | [8 empty] | 500 | 81 | [5 empty] | 419 | 513.7 | 94.7 | [5 empty] | 419
5.2.11 | Training for Guidance Officers | 47 |  |  | Nat | GCD | [8 empty] | 41 | 41 | [6 empty] | 54.7 | 54.7
5.2.12 | Implement Parents for Quality Education Program | 48 | 36. % of schools holding four parent and citizen meetings annually. 37. % of schools holding parent/teacher meetings. | 36. 90%. 37. 90% | School | PPD | [8 empty] | 27300 |  |  |  |  | 23300 | 4000 |  | 28900 |  |  |  |  | 24900 | 4000
5.2.15 | Emoluments and goods & services Standards Division |  |  |  |  | SD | [8 empty] | 8483 | 8483 | [6 empty] | 8483 | 8483
5.2.16 | Emoluments and goods & services Guidance & Counselling Division |  |  |  |  | GCD | [8 empty] | 1015.1 | 1015.1 | [6 empty] | 1015.1 | 1015.1
[14 empty] | Total | 286762.5 | 10279.5 | 0 | 38200 | 0 | 228200 | 4320 | 5763 | 202172.2 | 10709.2 | 0 | 33200 | 0 | 243700 | 4100 | 5763
[12 empty] | Summary |  |  | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
| Unfunded activities | [13 empty] | 289792.5 | 10279.5 | 0 | 38200 | 0 | 228200 | 7350 | 5763 | 205072.2 | 10709.2 | 0 | 33200 | 0 | 243700 | 7000 | 5763
[7 empty] | Implementation plan | [7 empty] | Budget & source
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | level | Responsible | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable |  | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
5.2.13 | Build and maintain school libraries |  | Refer to 1.2.6 FA 1 | [11 empty] | 0 | [7 empty] | 0 | [7 empty] | Included elsewhere in Action Plan
5.2.14 | Develop and publish standards for ECE centres |  | Refer to 1.1.3, FA 1 | ECCE Minimum Operating Standards |  | CDD/SD/DfCDR | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Included elsewhere in Action Plan

## FA 6
6 | Focus Area |  | System strengthening
6.1 | Communication, connectivity and information systems
50 | Improve communication and access to information across MoE and all levels of education
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable |  | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
6.1.1 | ICT systems national, regional, provincial and district | 50 | 50. % of provinces submitting EMIS data electronically | 60% |  | ICTD/EMIS | [8 empty] | 4405.4 | 225 |  | 4000 |  |  |  | 180.4 | 4429.2 | 248.8 |  | 4000 |  |  |  | 180.4
6.1.2 | Closed-User Group phone network | 50 |  |  |  | ICTD | [8 empty] | 500 | [6 empty] | 500 | 500 | [6 empty] | 500
6.1.3 | Emoluments and goods & services ICTD |  |  |  |  | ICTD | [8 empty] | 882.5 | 882.5 | [6 empty] | 882.5 | 882.5
[14 empty] | Total | 5787.9 | 1107.5 | 0 | 4000 | 0 | 0 | 0 | 680.4 | 5811.7 | 1131.3 | 0 | 4000 | 0 | 0 | 0 | 680.4
6.2 | Planning and coordination
51 | Improve planning
52 | Improve policy | [29 empty] | 4.6363 | 4.8308
53 | Improve coordination
54 | Monitor, evaluate, report and ensure accountability
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable |  | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
6.2.1 | Annual Operational and Financial Plan development |  | 1.8 Public expedenditure on education as % of GDP/government expenditure | 6.0% of GDP |  | PPD | [8 empty] | 510 | 10 |  |  |  |  | 500 |  | 10 | 10
6.2.2 | Support for provincial education plans | 51 |  |  |  | PPD | [8 empty] | 810 | [5 empty] | 810 |  | 5218.9 | 50 |  | 5000 |  |  |  | 168.9
6.2.3 | Publish National Education Policy Standards Framework | 52 |  |  |  | PPD | [8 empty] | 500 | [5 empty] | 500 |  | 500 | [5 empty] | 500
6.2.4 | Audit NDoE policies | 52 |  |  |  | PPD | [8 empty] | 450 | [5 empty] | 450 |  | 450 | [5 empty] | 450
6.2.5 | To disemminate inforamtion regarding education | 53 |  |  |  | CCLS | [8 empty] | 294.5 | 294.5 | [6 empty] | 294.5 | 294.5
6.2.6 | Train NDoE officers in policy development | 52 |  |  |  | PPD | [8 empty] | 50 | [5 empty] | 50 |  | 50 | [5 empty] | 50
6.2.7 | To conduct research and evaluation as required | 54 |  |  |  | RED | [8 empty] | 1391.2 | 170 |  |  |  |  | 1040 | 181.2 | 1278.4 | 147.2 |  |  |  |  | 950 | 181.2
6.2.8 | Donor alignment | 53 |  |  |  | PPD | [8 empty] | 1145.2 | 60 |  |  |  |  | 1000 | 85.2 | 1105.4 | 20.2 |  |  |  |  | 1000 | 85.2
6.2.9 | Annual school census & EMIS maintenance | 54 | 40. % of schools submitting school census data | 100% |  | EMIS | [8 empty] | 1000 | [5 empty] | 1000 |  | 1000 | [5 empty] | 1000 |  | For school inspection, please refer to FA 5
6.2.10 | MySchool data collection pilot | 54 |  |  |  | EMIS/ICTD | [8 empty] | 2000 |  |  | 1000 |  |  | 1000 |  | 2000 |  |  | 1000 |  |  | 1000
6.2.11 | To administer UNESCO activities | 53 |  |  |  | UNESCO | [8 empty] | 728.9 | 728.9 | [6 empty] | 728.9 | 728.9
6.2.12 | Provide coordination services inc library and Govt archives | 53 |  |  |  | GES | [8 empty] | 1310.25 | 1046.55 | [5 empty] | 263.7 | 1444.05 | 1180.35 | [5 empty] | 263.7
6.2.13 | Joint Education Sector Reviews | 54 | 49. NEP review and evaluation | Annual |  | RED | [8 empty] | 68.9 | [6 empty] | 68.9 | 38.9 | [6 empty] | 38.9
6.2.15 | PaBER & SABER capacity assessments | 52 | 48. Quality assessment of education policies | Established level |  | RED | [8 empty] | 50 | [5 empty] | 50 |  | 50 | [5 empty] | 50 |  | World Bank
6.2.16 | Intersectoral ECCE Policy | 66 | Please see FA 3
6.2.17 | National Education Plan development | 51 |  |  |  | PPD/RED | [8 empty] | 48 | 48 | [6 empty] | 1060 | 30 |  |  |  |  | 900 | 130
6.2.18 | To provide admin services to Sec and Min inc NEB |  |  |  |  | MS / Exec Wing | [8 empty] | 1196.7 | 882 | [5 empty] | 314.7 | 1340.9 | 1026.2 | [5 empty] | 314.7
6.2.19 | Emoluments and goods & services GES |  |  |  |  | GES | [8 empty] | 956.2 | 956.2 | [6 empty] | 956.2 | 956.2
6.2.20 | Emoluments and goods & services UNESCO |  |  |  |  | UNESCO | [8 empty] | 1414.9 | 1414.9 | [6 empty] | 1414.9 | 1414.9
6.2.21 | Emoluments and goods & services Exec Wing, Min Serv, NEB | [13 empty] | 1455.7 | 1455.7 | [6 empty] | 1456 | 1456
6.2.22 | Emoluments and goods & services CCLS |  |  |  |  | CCLS | [8 empty] | 553.5 | 553.5 | [6 empty] | 553.5 | 553.5
6.2.23 | Emoluments and goods & services PPD |  |  |  |  | PPD | [8 empty] | 1100 | 1100 | [6 empty] | 1100 | 1100
6.2.24 | Emoluments and goods & services OLA |  |  |  |  | OLA | [8 empty] | 1306.6 | 1306.6 | [6 empty] | 1306.6 | 1306.6
6.2.25 | Emoluments and goods & services Ad Coordination |  |  |  |  | Aid Coord | [8 empty] | 714.1 | 714.1 | [6 empty] | 714.1 | 714.1
6.2.26 | Emoluments and goods & services Govt archives |  |  |  |  | Archives | [8 empty] | 435.2 | 435.2 | [6 empty] | 435.2 | 435.2
6.2.27 | Emoluments and goods & services RED |  |  |  |  | RED | [8 empty] | 633.8 | 633.8 | [6 empty] | 633.8 | 633.8
[14 empty] | Total | 20123.65 | 11809.95 | 0 | 1000 | 0 | 0 | 6400 | 913.7 | 25140.25 | 12057.65 | 0 | 6000 | 0 | 0 | 5900 | 1182.6
6.3 | Financial management
55 | Establish government-wide Integrated Financial Management System (IFMS) with reporting requirements and timelines
56 | Improve NDoE asset management
57 | Ensure all claim and payment account processing complies with Public Finances (Management) Act
58 | Create transparent centralised and streamlined procurement system
59 | Establish single payroll system, with decentralised operation and national quality assurance
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
6.3.1 | IFMS training and operation | 55 | 43. % of quarterly operation and financial reports submitted on time and reporting on all budget activities. 3.6 % of education system budgets expended annually. | 43. 90%. 3.6. 90% | Nat | FD | [8 empty] | 0 | [7 empty] | 0
6.3.2 | Annual financial plans and reports | 55 | 47. Annual NDoE financial report submitted to DoF | Annually | Nat | FD/PPD | [8 empty] | 880 | 880 | [6 empty] | 1163.7 | 1163.7
6.3.3 | Internal audit | 57 | 46. % of advances and allowances fully acquitted | 100% | Nat | AD | [8 empty] | 173 | 173 | [6 empty] | 193 | 193
6.3.4 | Asset management strengthening | 56 |  |  | Nat | ProD | [8 empty] | 823.5 | 200 | [5 empty] | 623.5 | 1145.5 | 522 | [5 empty] | 623.5
6.3.5 | Administration of Procurement Operations | 58 |  |  | Nat | [9 empty] | 1331 | 1331 | [6 empty] | 1205.3 | 1205.3
6.3.6 | Procurement management strengthening | 58 |  |  | Nat | ProD | [8 empty] | 100 | [6 empty] | 100 | 100 | [6 empty] | 100
6.3.7 | Emoluments and goods & services FD | [13 empty] | 1818 | 1818 | [6 empty] | 1818 | 1818
6.3.8 | Emoluments and goods & services ProD | [13 empty] | 775.3 | 775.3 | [6 empty] | 775.3 | 775.3
6.3.9 | Emoluments and goods & services AD | [13 empty] | 1677 | 1677 | [6 empty] | 1677 | 1677
[14 empty] | Total | 7577.8 | 6854.3 | 0 | 0 | 0 | 0 | 0 | 723.5 | 8077.8 | 7354.3 | 0 | 0 | 0 | 0 | 0 | 723.5
6.4 | Human resources
60 | Improve staffing, teaching and public service | [14 empty] | 1915.9
61 | Improve efficiency of teacher employment | [14 empty] | 585.3 | 1330.6
62 | Improve public servant recruitment, appointment and succession planning | [14 empty] | 2403.3
63 | Improve school services
64 | Create accessible libraries, records and documents
65 | Transfer of NCDES to NCDC
[7 empty] | Implementation plan | [7 empty] | Budget & source
[7 empty] | 2019 |  |  |  | 2020 |  |  |  | 2019 | [7 empty] | 2020
| Activities | Strategy no. | NEP Indicator | NEP Target/deliverable | Level | Responsible | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Notes
6.4.1 | Update Human Resource Management Policy | 60 |  |  | Nat | HROD | [8 empty] | 50 | 50 | [6 empty] | 0
6.4.2 | Create Teacher Registration Board | 61 |  |  | Nat | TED/TSC | [8 empty] | 0 | [7 empty] | 0
6.4.3 | Establish TSC offices in all provinces | 61 |  |  | Prov | TSC | [8 empty] | 2461 | 2461 | [6 empty] | 2888.3 | 2888.3
6.4.4 | Teacher payroll management | 59 | 3.1 No. of teachers and school officials put back on payroll by end of April annually compared with March payroll & 3.2 Teaching position vacancies | 3.1 TBD (baseline 81%) 3.2 TBD | Nat | Payroll / TSC | [8 empty] | 1699.8 | 1285 | [5 empty] | 414.8 | 1761.8 | 1347 | [5 empty] | 414.8
6.4.5 | Teacher salaries | 59 | 45. % of teachers' salaries appropriation spent (through provincial budgets) | 100% | Prov | HROD/provinces | [8 empty] | 1201847.8 | 36903.8 |  | 1164244 |  |  | 700 |  | 1273216.668 | 39118.028 |  | 1234098.64
6.4.6 | Teacher leave fares | 61 |  |  | Prov | HROD/provinces | [8 empty] | 35021.1 | 6511.1 |  | 28510 |  |  |  |  | 37694.6 | 6511 |  | 31183.6
6.4.7 | Outsource public servant recruitment | 62 | 44. % of total national education system appropriations allocated to personal emoluments | 40% | Nat | HROD | [8 empty] | 40 | 40 | [6 empty] | 40 | 40
6.4.8 | Public servant professional development and appraisal | 62 |  |  | Nat | HROD | [8 empty] | 507.3 | 121.2 | [5 empty] | 386.1 | 635.1 | 249 | [5 empty] | 386.1
6.4.9 | Review of public servant housing | 62 |  |  | Nat | HROD | [8 empty] | 30 | 30 | [6 empty] | 30 | 30 | [6 empty] | For school inspection, please refer to FA 5
6.4.11 | Digitise records as part of Integrated Government Information System | 64 |  |  | Nat | [9 empty] | 110 | 110 | [6 empty] | 134 | 134
6.4.12 | Transfer NCDES to NCDC | 65 |  |  | Nat | NCD | TBD | [7 empty] | 87.5 | 87.5 | [6 empty] | 134 | 134
6.4.13 | Emoluments and goods & services HROD |  |  |  |  | HROD | [8 empty] | 2063.3 | 2063.3 | [6 empty] | 2063.3 | 2063.3
6.4.14 | Emoluments and goods & services NCDES |  |  |  |  | NCDES | [8 empty] | 600.1 | 600.1 | [6 empty] | 600.1 | 600.1
6.4.15 | Emoluments and goods & services Payroll. |  |  |  |  | Payroll | [8 empty] | 1506.4 | 1506.4 | [6 empty] | 1506.4 | 1506.4
6.4.16 | Emoluments and goods & services UNESCO |  |  |  |  | UNESCO | [8 empty] | 1284.9 | 1284.9 | [6 empty] | 1284.9 | 1284.9
6.4.17 | Emoluments and goods & services TSC |  |  |  |  | TSC | [8 empty] | 3069 | 3069 | [6 empty] | 3069 | 3069
[14 empty] | Total | 1250378.2 | 56123.3 | 0 | 1192754 | 0 | 0 | 700 | 800.9 | 1325058.168 | 58975.028 | 0 | 1265282.24 | 0 | 0 | 0 | 800.9
3461.9
[11 empty] | Summary |  |  |  | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
[15 empty] | 1283867.55 | 75895.05 | 0 | 1197754 | 0 | 0 | 7100 | 3118.5 | 1364087.918 | 79518.278 | 0 | 1275282.24 | 0 | 0 | 5900 | 3387.4
Unfunded activities
| Activities | Strategy No | NEP Indicator | NEP Target/deliverable | level | Responsible
6.2.14 | NDoE Annual Report |  | 3.7 NDoE annual report tabled in Parliament on time with 100% coverage of budget activities | Annual |  | RED | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Does not require funding - routine work
6.4.10 | Improved school registration |  |  |  |  | GES | [8 empty] | 0 | [7 empty] | 0 | [7 empty] | Does not require funding - routine work

## Summary
| Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap | Total | Recurr. | Dev. | Prov. | Dept | TFF | DP | Gap
FA 1 | 585572.6402 | 2735.2 | 0 | 395065.8 | 0 | 180100 | 4515.0402 | 3156.6 | 578245.2 | 1447.1 | 0 | 377565.8 | 0 | 192100 | 4625.7 | 2506.6
FA 2 | 75644.95 | 22477.45 | 15000 | 8000 | 0 | 0 | 26860 | 3307.5 | 74191.05 | 23293.55 | 15000 | 8000 | 0 | 0 | 24590 | 3307.5
FA 3 | 337147.9667 | 41286.3 | 0 | 53151.9 | 22.4 | 174672 | 44581.6667 | 23433.7 | 321259.4 | 42690.2 | 0 | 53151.9 | 23.9 | 186482 | 44144.6667 | 23433.4
FA 4 | 94831.358 | 36083.75 | 23000 | 2000 | 304 | 0 | 29983.008 | 3460.6 | 108647.74 | 37877.5 | 22000 | 2000 | 324.5 | 0 | 42985.14 | 3460.6
FA 5 | 289792.5 | 10279.5 | 0 | 38200 | 0 | 228200 | 7350 | 5763 | 205072.2 | 10709.2 | 0 | 33200 | 0 | 243700 | 7000 | 5763
FA 6 | 1283867.55 | 75895.05 | 0 | 1197754 | 0 | 0 | 7100 | 3118.5 | 1364087.918 | 79518.278 | 0 | 1275282.24 | 0 | 0 | 5900 | 3387.4
| 2666856.9649 | 188757.25 | 38000 | 1694171.7 | 326.4 | 582972 | 120389.7149 | 42239.9 | 2651503.508 | 195535.828 | 37000 | 1749199.94 | 348.4 | 622282 | 129245.5067 | 41858.5

## DFAT (hidden)
Budget allocation by NEP strategy (K mills) | [12 empty] | elem |  |  |  | prim |  |  |  | sec |  |  |  | voc | [8 empty] | Tr colls |  |  |  |  | Tech |  |  |  | Other
[34 empty] | 2018 | 2019 | 2020 | 2021 |  | 2018 | 2019 | 2020 | 2021
Strat # | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | [5 empty] | 2018 | 2019 | 2020 | 2021 | 2018 | 2019 | 2020 | 2021 | 2018 | 2019 | 2020 | 2021 | 2018 | 2019 | 2020 | 2021 |  | 2018 | 2019 | 2020 | 2021
1 |  |  |  | 4 | 4 | 4 | 4 | [5 empty] | 1.6608 | 1.6608 | 1.6608 | 1.6608 | 1.9186 | 1.9186 | 1.9186 | 1.9186 | 0.34577 | 0.34577 | 0.34577 | 0.34577 | 0.074875 | 0.074875 | 0.074875 | 0.074875 | OK | 4 | 4 | 4 | 4
2 | [12 empty] | 2018: 0; 2018: 0; 2018: 0 | OK | 0 | 0 | 0 | 0
3 |  |  |  | 0.6 | [8 empty] | 0.24912 | 0 | 0 | 0 | 0.28778 | 0 | 0 | 0 | 0.051865 | 0 | 0 | 0 | 0.011231 | 0 | 0 | 0 | OK | 0.6 | 0 | 0 | 0
4 |  |  |  | 0.6 | [8 empty] | 0.24912 | 0 | 0 | 0 | 0.28778 | 0 | 0 | 0 | 0.051865 | 0 | 0 | 0 | 0.011231 | 0 | 0 | 0 | OK | 0.6 | 0 | 0 | 0
5 |  |  |  | 0.6 | [8 empty] | 0.24912 | 0 | 0 | 0 | 0.28778 | 0 | 0 | 0 | 0.051865 | 0 | 0 | 0 | 0.011231 | 0 | 0 | 0 | OK | 0.6 | 0 | 0 | 0
6 |  |  |  | 0.7 | [8 empty] | 0.105 | 0 | 0 | 0 | 0.28 | 0 | 0 | 0 | 0.28 | 0 | 0 | 0 | 0.035 | 0 | 0 | 0 | OK | 0.7 | 0 | 0 | 0
7 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
9 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
10 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
11 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
12 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
13 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
14 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
66
| 0 | 0 | 0 | 6.5 | 4 | 4 | 4 | [21 empty] | not | 0 | 0 | 0 | 0
15 |  |  |  | 0.075 | [24 empty] | OK | 0.075 | 0 | 0 | 0 | 0.075 | 0 | 0 | 0
16 | [28 empty] | OK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  |  |  | 4.135 | 4.135 | 4.135 | 4.05 | [21 empty] | OK | 4.135 | 4.135 | 4.135 | 4.05 | 4.135 | 4.135 | 4.135 | 4.05
18 |  |  |  | 3.72 | 3.65 | 3.65 | 3.65 | [21 empty] | OK | 3.72 | 3.65 | 3.65 | 3.65 | 3.72 | 3.65 | 3.65 | 3.65
19 | [28 empty] | OK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  |  |  | 4.35 | 4.35 | 4.35 | 4.35 | [5 empty] | 1.8061 | 1.8061 | 1.8061 | 1.8061 | 2.0864 | 2.0864 | 2.0864 | 2.0864 | 0.37602 | 0.37602 | 0.37602 | 0.37602 | 0.081426 | 0.081426 | 0.081426 | 0.081426 | OK | 4.35 | 4.35 | 4.35 | 4.35
67
| 0 | 0 | 0 | 12.28 | 12.135 | 12.135 | 12.05 | [21 empty] | not | 0 | 0 | 0 | 0
21 |  |  |  | 4.7657 | 4.7 | 4.7 | 4.65 | [5 empty] | 0.95314 | 0.94 | 0.94 | 0.93 | 1.9063 | 1.88 | 1.88 | 1.86 | 1.2709 | 1.2533 | 1.2533 | 1.24 | 0.63543 | 0.62667 | 0.62667 | 0.62 | OK | 4.7657 | 4.7 | 4.7 | 4.65
22 |  |  |  | 3 | 3 | 3 | 3 | [5 empty] | 1.2456 | 1.2456 | 1.2456 | 1.2456 | 1.4389 | 1.4389 | 1.4389 | 1.4389 | 0.25933 | 0.25933 | 0.25933 | 0.25933 | 0.056156 | 0.056156 | 0.056156 | 0.056156 | OK | 3 | 3 | 3 | 3
23 |  |  |  | 0.45 | 0.45 | 0.45 | 0.45 | [5 empty] | 0.18684 | 0.18684 | 0.18684 | 0.18684 | 0.21584 | 0.21584 | 0.21584 | 0.21584 | 0.038899 | 0.038899 | 0.038899 | 0.038899 | 0.0084234 | 0.0084234 | 0.0084234 | 0.0084234 | OK | 0.45 | 0.45 | 0.45 | 0.45
24 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
25 |  |  |  | 12 | 2 | 2 | 2 | [5 empty] | 2018: 12; 2019: 2; 2020: 2; 2021: 2 | OK | 12 | 2 | 2 | 2
26 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
27 | [10 empty] | e |  | 2018: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
28 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
29 |  |  |  | 4.35 | 4.35 | 4.35 | 4.35 | [5 empty] | 2018: 4.35; 2019: 4.35; 2020: 4.35; 2021: 4.35 | OK | 4.35 | 4.35 | 4.35 | 4.35
30 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
31 |  |  |  | 0.6 | 0.6 | 0.6 | 0.6 | [5 empty] | 0.24912 | 0.24912 | 0.24912 | 0.24912 | 0.28778 | 0.28778 | 0.28778 | 0.28778 | 0.051865 | 0.051865 | 0.051865 | 0.051865 | 0.011231 | 0.011231 | 0.011231 | 0.011231 | OK | 0.6 | 0.6 | 0.6 | 0.6
| 0 | 0 | 0 | 25.1657 | 15.1 | 15.1 | 15.05 | [21 empty] | not | 0 | 0 | 0 | 0
32 |  |  |  | 0.25 | [8 empty] | 2018: 0.22109; 2019: 0; 2020: 0; 2021: 0 | OK | 0.25 | 0 | 0 | 0 | [5 empty] | 0.028914 | 0 | 0 | 0
33 |  |  |  | 0.25 | [8 empty] | 2018: 0.22109; 2019: 0; 2020: 0; 2021: 0 | OK | 0.25 | 0 | 0 | 0 | [5 empty] | 0.028914 | 0 | 0 | 0
34 |  |  |  | 0.25 | [8 empty] | 2018: 0.22109; 2019: 0; 2020: 0; 2021: 0 | OK | 0.25 | 0 | 0 | 0 | [5 empty] | 0.028914 | 0 | 0 | 0
35 |  |  |  | 12.25 | 2 | 2 | 2 | [5 empty] | 2018: 10.8332; 2019: 1.7687; 2020: 1.7687; 2021: 1.7687 | OK | 12.25 | 2 | 2 | 2 | [5 empty] | 1.4168 | 0.23132 | 0.23132 | 0.23132
36 |  |  |  | 0.25 | [24 empty] | OK | 0.25 | 0 | 0 | 0 | [5 empty] | 0.25 | 0 | 0 | 0
37 |  |  |  | 0.25 | [8 empty] | 2018: 0.22109; 2019: 0; 2020: 0; 2021: 0 | OK | 0.25 | 0 | 0 | 0 | [5 empty] | 0.028914 | 0 | 0 | 0
38 |  |  |  | 14.375 | 2 | 2 | 2 | [21 empty] | OK | 14.375 | 2 | 2 | 2 | [5 empty] | 14.375 | 2 | 2 | 2
39 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
40 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
41 | [12 empty] | 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
42 | [28 empty] | OK | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 27.875 | 4 | 4 | 4 | [21 empty] | not | 0 | 0 | 0 | 0
[29 empty] | OK | 0 | 0 | 0 | 0
43 |  |  |  | 3.15 | 3.15 | 3 | 3 | 3.15 | 3 |  |  |  | 1.3079 | 1.3079 | 1.2456 | 1.2456 | 1.5109 | 1.5109 | 1.4389 | 1.4389 | 0.27229 | 0.27229 | 0.25933 | 0.25933 | 0.058964 | 0.058964 | 0.056156 | 0.056156 | OK | 3.15 | 3.15 | 3 | 3
44 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
46 |  |  |  | 0.15 | 0.15 | [7 empty] | 0.06228 | 0.06228 | 0 | 0 | 0.071946 | 0.071946 | 0 | 0 | 0.012966 | 0.012966 | 0 | 0 | 0.0028078 | 0.0028078 | 0 | 0 | OK | 0.15 | 0.15 | 0 | 0
47 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
48 |  |  |  | 4 | 4 | 4 | 4 | [5 empty] | 1.6608 | 1.6608 | 1.6608 | 1.6608 | 1.9186 | 1.9186 | 1.9186 | 1.9186 | 0.34577 | 0.34577 | 0.34577 | 0.34577 | 0.074875 | 0.074875 | 0.074875 | 0.074875 | OK | 4 | 4 | 4 | 4
49 | [10 empty] | e |  | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 7.3 | 7.3 | 7 | 7 | [21 empty] | not | 0 | 0 | 0 | 0
50 |  |  |  | 6.655 | [24 empty] | OK | 6.655 | 0 | 0 | 0 | [9 empty] | 6.655 | 0 | 0 | 0
51 |  |  |  | 1 | 1 | 1 | 1 | [21 empty] | OK | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1
52 |  |  |  | 1 | 1 | 1 | 1 | [21 empty] | OK | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1
53 |  |  |  | 1 | 1 | 1 | 1 | [21 empty] | OK | 1 | 1 | 1 | 1 | [9 empty] | 1 | 1 | 1 | 1
54 |  |  |  | 3 | 3 | 3 | 3 |  |  |  | 1160 | [17 empty] | OK | 3 | 3 | 3 | 3 | [9 empty] | 3 | 3 | 3 | 3
55 |  |  |  | 2.655 | [6 empty] | 282.5 | [17 empty] | OK | 2.655 | 0 | 0 | 0 | [9 empty] | 2.655 | 0 | 0 | 0
56 |  |  |  | 2.655 | [24 empty] | OK | 2.655 | 0 | 0 | 0 | [9 empty] | 2.655 | 0 | 0 | 0
57 |  |  |  | 2.655 | [24 empty] | OK | 2.655 | 0 | 0 | 0 | [9 empty] | 2.655 | 0 | 0 | 0
58 |  |  |  | 2.655 | [24 empty] | OK | 2.655 | 0 | 0 | 0 | [9 empty] | 2.655 | 0 | 0 | 0
59 | [28 empty] | OK | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0
60 | [12 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
61 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OK | 0 | 0 | 0 | 0
62 | [28 empty] | OK | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0
63 |  |  |  | 0.7 | 0.7 | 0.7 | 0.7 | [21 empty] | OK | 0.7 | 0.7 | 0.7 | 0.7 | [9 empty] | 0.7 | 0.7 | 0.7 | 0.7
64 | [10 empty] | e |  | 2018: 0; 2019: 0; 2020: 0; 2021: 0; 2018: 0; 2019: 0; 2020: 0; 2021: 0 | OK | 0 | 0 | 0 | 0
65 | [28 empty] | OK | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 23.975 | 6.7 | 6.7 | 6.7 | [21 empty] | not | 0 | 0 | 0 | 0
Other | [28 empty] | OK | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0
|  |  |  | 103.0957 | 49.235 | 48.935 | 48.8 | [21 empty] | not
[29 empty] | OK | 0 | 0 | 0 | 0
Total | [28 empty] | OK | 0 | 0 | 0 | 0
|  |  |  | 3710.2 | [8 empty] | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 7.93 | 7.785 | 7.785 | 7.7 | 0 | 16.1575 | 2.2313 | 2.2313 | 2.2313 | 23.975 | 6.7 | 6.7 | 6.7
Other contributions in K'000s | [28 empty] | OK | 0 | 0 | 0 | 0
[13 empty] | 2018 | 2019 | 2020 | 2021
[10 empty] | #DIV/0! | 1.0114 | Elem | 2018: #DIV/0!; 2019: #DIV/0!; 2020: #DIV/0!; 2021: #DIV/0!; 2018: #DIV/0!
DfRCD | [9 empty] | #DIV/0! | 1.6064 | Prim | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 18938 | 16789 | 317.9501 |  | 0 |  | 0 |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  |  | #DIV/0! | 1.8314 | Sec | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 26382 | 29544 | 779.4298 |  | 0 |  | 0
11505 | Early Childhood | 16.5 | 17.9 | 23.2 | 22.4 | 23.9 | 23.9 |  |  | #DIV/0! | 2.3874 | Voc | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | 31589 | 5298 | 167.3585 |  | 0 |  | 0
[10 empty] | #DIV/0! |  | Tr Colls | 7.93 | 7.785 | 7.785 | 7.7 | #DIV/0! |  | 28985.5 | 1274 | 36.9275 |  | 0 |  | 0
DHERST | [9 empty] | #DIV/0! |  | Tech | 2018: 16.1575; 2019: 2.2313; 2020: 2.2313; 2021: 2.2313; 2018: #DIV/0!
12182 | TVET Division | 250.6 | 306.9 | 313.9 | 304 | 324.5 | 324.5 |  |  | #DIV/0! |  | Other | 2018: 23.975; 2019: 6.7; 2020: 6.7; 2021: 6.7; 2018: #DIV/0!; 2018: 1301.6659; 2019: 0; 2018: 0
10440 | TESAS | 51236 | 47860 | 71626.5 | 69355.9 | 74045.3 | 74031.7 |  |  | #DIV/0! |  |  | 2018: #DIV/0!; 2019: #DIV/0!; 2020: #DIV/0!; 2021: #DIV/0!
Development budget
21074 | SMART Specialisation | 9698.7 | 5000 | 10000 | 10000 | 10000 | 10000
22644 | Tech / BC Rehab | 3000 | 9000 | 12000 | 12000 | 12000 | 12000 | [5 empty] | 2018: #DIV/0!; 2019: #DIV/0!; 2020: #DIV/0!; 2021: #DIV/0!
22646 | Tr College rehab | 3000 | 5000 | 15000 | 15000 | 15000 | 15000
| 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Focus area 1 | 0 | 0 | 0 | 6.5 | 4 | 4 | 4
Focus area 2 | 0 | 0 | 0 | 12.28 | 12.135 | 12.135 | 12.05
Focus area 3 | 0 | 0 | 0 | 25.1657 | 15.1 | 15.1 | 15.05
Focus area 4 | 0 | 0 | 0 | 27.875 | 4 | 4 | 4
Focus area 5 | 0 | 0 | 0 | 7.3 | 7.3 | 7 | 7
Focus area 6 | 0 | 0 | 0 | 23.975 | 6.7 | 6.7 | 6.7
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 103.0957 | 49.235 | 48.935 | 48.8

## Tbles for plan (hidden)
|  | 582.416 | 575.6386
|  | 71.3375 | 70.8835
|  | 285.0476 | 297.826
|  | 92.3708 | 105.1871
|  | 284.0295 | 199.3092
|  | 1280.7491 | 1360.8005
|  | 2595.9504 | 2609.645
Tble 82
|  | 2019 | 2020
| FA 1 | 582.416 | 575.6386 |  |  |  | 2018 | 2019 | 2020 | 2021
| FA 2 | 71.3375 | 70.8835 |  |  | Elem | 722.9 | 729 | 757.8 | 767.2
| FA 3 | 285.0476 | 297.826 |  |  | Prim | 1768.3 | 1791 | 1847.4 | 1870.1
| FA 4 | 92.3708 | 105.1871 |  |  | Sec | 456.4 | 458.8 | 474.2 | 479
| FA 5 | 284.0295 | 199.3092 |  |  | Voc | 125.1 | 105.6 | 108.7 | 109.8
| FA 6 | 1280.7491 | 1360.8005 |  |  | Tr Colls | 41.5 | 40.8 | 42 | 41.9
|  | 2595.9504 | 2609.645 |  |  | Tech | 56.8 | 47.1 | 48.1 | 48.1
[6 empty] | Other | 61.1 | 61 | 61.1 | 61.2
Table 83 | [6 empty] | 3231.9 | 3233.4 | 3339.3 | 3377.3
| Elem | 596.5351 | 603.2545
| Prim | 1465.5615 | 1470.6419 |  |  | Elem | 22.8% | 22.98% | 23.12% | 23.14%
| Sec | 375.4325 | 377.4918 |  |  | Prim | 55.77% | 56.46% | 56.35% | 56.39%
| Voc | 86.4117 | 86.5318 |  |  | Sec | 14.39% | 14.46% | 14.47% | 14.44%
| Tr Colls | 33.3863 | 33.4345 |  |  | Voc | 3.945% | 3.329% | 3.316% | 3.311%
| Tech | 38.5416 | 38.2905 |  |  | Tr Colls | 1.309% | 1.286% | 1.281% | 1.264%
|  | 2595.8686 | 2609.645 |  |  | Tech | 1.791% | 1.485% | 1.467% | 1.45%
|  |  |  | 943622 | 925469 |  | 100% | 100% | 100% | 100%
Table 84 |  |  |  | 1099293 | 1146088
|  |  |  | 241489 | 263906
| Elem | 632.1759 | 651.8366
| Prim | 1333.1855 | 1283.1841
| Sec | 1554.6567 | 1430.4025
Table 85
|  | 2.7352 | 1.4471
|  | 22.4775 | 23.2935
|  | 41.2863 | 42.6902
|  | 36.0838 | 37.8775
|  | 10.2795 | 10.7092
|  | 75.895 | 79.5183
|  | 188.7572 | 195.5358
Table 86
| FA1 | 180.1 | 192.1
| FA2 | 0 | 0
| FA3 | 174.672 | 186.482
| FA4 | 0 | 0
| FA5 | 228.2 | 243.7
| FA6 | 0 | 0
|  | 582.972 | 622.282
Table 87
| FA1 | 395.0658 | 377.5658
| FA2 | 8 | 8
| FA3 | 53.1519 | 53.1519
| FA4 | 2 | 2
| FA5 | 38.2 | 33.2
| FA6 | 1197.754 | 1275.2822
|  | 1694.1717 | 1749.1999
Table 89
| FA1 | 4.515 | 4.5257
| FA2 | 40.86 | 39.59
| FA3 | 44.5817 | 44.1447
| FA4 | 53.983 | 64.9851
| FA5 | 7.35 | 7
| FA6 | 7.1 | 6
|  | 158.3898 | 166.2455
Table 90
| Recurrent | 188.7572 | 195.5358
| Prov | 1694.1717 | 1749.1999
| TFF | 582.972 | 622.282
| Other Depts | 0.3264 | 0.3484
| Projects | 158.3898 | 166.2455
|  | 2624.6171 | 2733.6117
Table 91
| FA1 | 2.5066 | 2.5066
| FA2 | 3.3075 | 3.3075
| FA3 | 23.4337 | 23.4334
| FA4 | 3.4606 | 3.4606
| FA5 | 5.763 | 5.763
| FA6 | 3.1185 | 3.3874
|  | 41.5899 | 41.8585
Table 97
| Recurrent | 230.3471 | 237.3943
| Prov | 1694.1717 | 1749.1999
| TFF | 582.972 | 622.282
| Other Depts | 0.3264 | 0.3484
| Projects | 158.3898 | 166.2455
| New projects | 260.4 | 346.8
| Total | 2926.607 | 3122.2702
| gap | 10.32% | 12.45%